## Tickets-January-04-2022
Actual Cost | Assets Number | Category | Classification | Closed Time | Created Time | Date of Services | Sold Amount | Department | Description | Ticket Id | Due by Time | Employee ID | ETA Date | First Response Time (in Hrs) | First Response Status | Initial Response Time | Formatting the Hard drive twice | Fusion Module | Group | Impact | Customer interactions | Item | Mantis ID Ref. | Agent Name | NBV | Number of Records | Oracle SR | ORC L2 Agents | UPDATE AT 20220103 | UPDATE AT 20220104 | Agent interactions | Priority | Reason for Closed/ Resolved | Reference Number - Ø±Ù‚Ù… Ø§Ù„Ù…Ø±Ø¬Ø¹ | Organizational Unit | Request Codes | Request Type | Requested Quantity - SCM | Requested Value - SCM | Requester Email | Requester Mobile Number | Requester Name | Resolution Status | Resolution Time (in Hrs) | Resolved Time | Agent | Source | Status | Region | Store | Sub-Category | Subject | Supplier number | Responsible Employee - Ù…Ø¹Ù„ÙˆÙ…Ø§Øª Ø§Ù„Ù…ØªØ³Ø¨Ø¨ Ø¨Ø§Ù„Ù…Ø®Ø§Ù„ÙØ© | Survey Result | Tags | Type | Time Tracked | Total amount | Last Updated Time | Urgency | Vendor Name | Final Violation Value - Ù‚ÙŠÙ…Ø© Ø§Ù„Ù…Ø®Ø§Ù„ÙØ© Ø§Ù„Ù†Ù‡Ø§Ø¦ÙŠØ© Ø¥Ù† ÙˆØ¬Ø¯Øª | What's the impact?
|  | Retail | Enhancement Related |  | 2021-09-02 16:59 |  |  | Information Technology | Pre Go_live (PGL) Defect 1456 HPQC HPQC raised by: Anu MyService Raised by: Ricardo Silva Test Instance[11549] : [1]UAT_TS0118_TC0005 Validate Account Payable for RTV in FUSION The document is fully posted in IMCS and RFI, but not available in Fusion There seems to be an issue on the Fusion side that needs to be clarified. Please check with Fusion team what is the error given there. Ricardo Filipe da Silva <oracle_rsilva>, 06/07/2021: Svyatoslav Tezin added a comment As I've already mentioned, the error need to be analyzed and clarified from the Fusion side. Please assign to Panda to analyse the error in finance. Thanks, Slava ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/6/2021: As agreed ways of working mail shared, assigning to Ricardo ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 06/07/2021: Svyatoslav Tezin added a comment - 31 minutes ago Hi, Robert Viner did validation in RFI and concluded that the supplier used was not initiated in RFI: 4081 AL BAYADER INTERNATIONAL LLC & site name AL BAYADER INTERNATIONAL LLC-10153 Sandeep Kulkarni analyzed from Fusion side the reason the supplier was not initiated in RFI: Only Supplier is created and site has failed because Supplier name in the site data file is not matching with Supplier header The team is working on resolution Hi Ricardo Silva, Next action is at Panda to provide the list of corrected supplier to Fusion team, for more details please refer to the attached email from Alejandro: FW FUSION ENVIRONMENT Post Refresh Activities - Functional.msg Thanks, Slava @Anu can you help with this request? ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/7/2021: Hi Farag, Can you provide the details ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/7/2021: Assigning defect to Oracle as per attached mail communication ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 08/07/2021: Svyatoslav Tezin added a comment The analysis is concluded: This supplier is not one of the migrated suppliers, this test case should be performed using only migrated suppliers. For further details on the migrated suppliers please contact Alejandro Pozo from Oracle Fusion team. Ready for re-test (using a migrated supplier) ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/8/2021: Moving the defect to Ready for test ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/11/2021: New RTV created today attached ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/12/2021: New RTV is also available in Fusion and defect reopened Screenshot attached ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 12/07/2021: Please coordinate with the Fusion team. Thank you ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/12/2021: RTV seems to be not available in RMFCS. Please help to check ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 12/07/2021: Tiago Marques added a comment Hi Ricardo Silva , RTV events created from Manhattan was published into MFCS but it's in error on RIB-RMS Hospital with the error description "RMSSUB_RTV.CONSUME(?,?,?,?)}: [E] Supplier does not allow items to be returned.". The supplier doesn't allow RTV. supplier_site_315379 ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/12/2021: Guna / Rajesh - Can you help to provide few suppliers with RTV enabled in RMFCS so that we can ask Manhattan team to create RTV again? ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/12/2021: Being retested Vendor Name Supplier Number Supplier site id FAMILY FOOD SUPPLY CO. 10585 911255 ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/13/2021: Fahad - The RTV allowed flag gets downloaded from RMFCS to MAnhattan and Manhattan will use that flag to allow or not allow the RTV to be initiated in Manhattan based on this flag. Was this flag changed in RMFCS after the RTV was initiated in Manhattan? Is the MOD in Manhattan there to check this flag? Was RMFCS and Manhattan flag aligned or are they different? Jamal - which field you are referring too, as i dont remember we have any field integrated from RMFCS if the RTV is allowed or not also we don't have any such customisation in WMS, attached the mapping document for reference Fahad - This is the returnable flag at supplier level and you had mentioned yourself that this flag is used when RTV is initiated from Manhattan and there is a customization to check for this flag and then allow initiation of RTV from Manhattan. It's not in RTV interface from RMFCS. It should be there in supplier master download from RMFCS. Jamal - we said that operation they will check if the vendor is returnable in RMFCS and accordingly they will flag the vendor in WMS than they will be allowed to return to the supplier, but from above what i understood that the RTV did not reach WMS at all Fahad - mentioned above is the the returnable flag in RMFCS is marked to not allow RTVs but an RTV was created/initiated from Manhattan and it got rejected in RMFCS as Rib checks returnable flag. So are you saying we don't have this flag downloaded in vendor interface and there is no check in Manhattan while actually initiating RTV from Manhattan? What the manual check was if the supplier delivers that item or not and not the flag check Jamal - we are not getting any flag that defines a vendor if its returnable or not from RMFCS Fahad - I am pretty sure this is what you had explained to me and Khadeer. Let's discuss tomorrow. If we don't have this flag then we should not allow RTV initiation from Manhattan at all and that option should be blocked. All RTVs should be created from RMFCS. By the way I am talking about line 78 from the mapping sheet with field name ASRTCD (Returns Policy Code). Is this not mapped to any field of Manhattan ? Jamal - as I mentioned and I am sure that we said that ops will check and accordingly will update the flag in wms under vendor table, and during my absence in the last KT session I got an information from the team that a discussion was raised for not initiating the rtv from MA Fahad - [1:22 PM] Fahad Gulzar Antonio Romualdo (Guest), David Ferreira, In the below mapping of supplier master from RMFCS to Manhattan in K2 file, why is the sups.ret_allow_ind not mapped to field ASRTCD? This is a straightforward mapping to send returns code from RMFCS to Manhattan. Can this be added because we have a customization to check this flag in Manhattan before allowing to create RTVs. The flag is supposed to be manually updated by user before creating RTV which does not make sense. If this comes through integration then it will block user from creating RTV if the value in RMFCS is 'N'. TARGET TYPE NAME FLAT FILE POSITION FIELD LENGTH DESCRIPTION MANDATORY COMMENTS SOURCE TYPE NAME DATA TYPE MAPPING/FILTERING RULES COMMENTS Flat file, fixed length ASRTCD 915 1 Returns Policy Code David - its possible to add the field there but that would imply some changes in the OIC and in the DB obejct to return that field. So its a CR. What is the criticallity for this? We can estimate and share and then see what can be done about its possible delivery. Can I ask the team for an estimation and formalize the CR? This will have impacts in the regular integration and also the full export. Fahad - This is an ask from DC and Manhattan team. Please go ahead and add to CR list. We can discuss on criticality as part of the CR discussion. My suggestion is to not allow DC users to create or initiate RTVs in Manhattan directly until this is delivered and all RTVs to be created from RMFCS till then because there is a risk of RTVs being rejected in RIB like it happened in above test since Manhattan is not checking this flag and depending on user to update this flag manually in Manhattan and then checking. So I am sure no one will manually update this flag and take care of this process. Sarah - Hi Fahad and thanks for the heads up. When we delivered training on RTV's in RMFCS to the key users in January, we were advised that there were no scenarios where RTV's would be done anywhere other than SIM or Manhattan. Very happy to support anything that needs to be done, but 2 call outs 1) we need to ensure that the DLS for DC team is re-validated on the basis of doing RTV in RMFC 2) we need to bring RMFCS RTV back into the scope of training delivery for August. Please advise when you are aligned on the solution and the change team can follow this up. Regards Sarah Dev Fahad - Technically both integrations are working and both possibilities are there but this returnable flag not going to Manhattan or not mapped to Manhattan is a risk so I advise to use RMFCS route till we get this fixed. This mapping most probably will not happen in time for GO LIVE so we need to re-initiate the RMFCS process to be on safe side and not see any rejections. ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/13/2021: Changing it as CR as discussed in triage Fahad - Please test this with a supplier with same flags in RMFCS and Manhattan. Please keep defect 1456 open for tracking CR and getting alignment from business not to use the Manhattan RTV functionality till the update is delivered. If workaround is accepted we can keep defect at low priority for tracking the CR delivery. ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 22/07/2021: John Jones: Hi Fahad Regarding this defect raised during UAT (1456) which is subsequently viewed as a change (CR), I wanted to confirm that we can only consider this for post R2 go-live (e.g. R2B scope to be delivered after go-live), given we are now almost at the end of UAT and need to freeze the code going into cutover. We have captured this in the CR log for tracking (CR #52). Regards | 706036 | 2022-01-03 14:49 |  |  | 421:25 | SLA Violated | 2021-11-08 15:24 | FALSE |  | Integration Vendor Support Group | Low | 1 |  | 36805 | David Machado |  |  | CR #52 / SR 3-27673787911 | Luis Martins |  |  | 11 | Low | CR consider for post R2 go-live |  | Savola Tower |  |  |  |  | integrationpt@panda.com.sa |  | Integration Project Team |  |  |  | RIB Vendor Support | Phone | Ready for Deployment â€“ Non Prod |  |  | RMS | PGL - Panda Issue 1456 - The document is fully posted in IMCS and RFI, but not available in Fusion (RTV creation from Manhattan not reaching Fusion/RMFCS) |  |  |  | CR #52,3-27673787911 - 22523831 | Incident | 0:00 |  | 2021-12-28 13:21 | Low |  |  | All Locations
|  | Retail |  |  | 2021-09-02 18:54 |  |  | Information Technology | Pre Go_live HPQC 1461 defect HPQC raised by: Anu MyService raised by: Ricardo Silva Transfer create from existing allows approval of transfer with quantity = 0 the SR is raised to port the bug fix to v19 SR : 3-26374302851, David - Integration layer is not performing this validation since it expects the system (MFCS) to ensure no transfer is approved with a qty of zero. After talking with the team this scenario seems to have origin in a transfer that was created from existing (where the transfer used as basis had the tsf qty set to 0 driven by the qty cancelled). In this case this seems to be a bug in MFCS which allows the approval in this particular scenario (when simply creating a new transfer in MFCS and adding items, a validation is performed against the qty). Looking at MOS there seems to be already a similar bug that was fixed in a previous version but in the v19 it seems this has been reintroduced. As such this must be addressed as an SR Ricardo Filipe da Silva <oracle_rsilva>, 07/07/2021: Manon Brard added a comment We are waiting for business confirmation that the functionality 'create from existing' will not be used in Panda (MUT is the main tool be used for transfer creation) in order to reduced severity to 4. At the moment this issue is not causing impact on the legacy system integration. Only issue is with the SOStatus (Interface ID236) which is moving the transfer in status 'Selected' to prevent edit. If this issue occurs, Panda team should be able to log into RIB hospital and delete the lines with error "quantity cannot be null" for the rest of the message to be processed. ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/25/2021: Changing to S4 | 706055 | 2021-09-09 12:00 |  |  | 135:00 | SLA Violated | 2021-09-23 17:07 | FALSE |  | RMFCS Vendor Support | Low | 1 |  | 38105 | Manon Brard |  |  | SR 3-26374302851 - BUG_33410682 | Carlos Costa | No status changes | No status changes | 33 | Low | Agreed To be deployed after go-live Can you schedule a meeting with Panda and Oracle to clarify this issue |  | Savola Tower |  |  |  |  | rmfcsptassets@panda.com.sa |  | RMFCS Project Team |  |  |  | No Agent | Phone | Pending With Vendor |  |  | RMS | PGL - Panda Issue 1461 - Transfer create from existing allows approval of transfer with quantity = 0 [SR 3-26374302851] |  |  |  | SR 3-26374302851,bug_33410682,3-26374302851 - 22438127 | Incident | 0:00 |  | 2021-12-28 13:24 | Low |  |  | All Locations
|  | Retail | Enhancement Related |  | 2021-09-02 19:38 |  |  | Information Technology | Pre Go Live defect 1497 HPQC HPQC raised by: panda_jamalw MyService: raised by ricardo silva Faced an issue in case an RTV was created in MA holding an item with more than one reason code, the qty is getting doubled Item: 144685 return qty under reason code "D" was 480 return qty under reason code "Q" was 240 total returned was 720 while the host system get updated with 720 under reason code "D" and another 720 under reason "Q" attached all the evidences Jamal Wehbe <panda_jamalw>, 7/26/2021: [3:15 PM] Antonio Romualdo (Guest) Qadri Mohd Hussain, thank you for your reply early on, in the RTV (ID225). Based on the Invoice Files, for the PKT_CTRL_NBR = 013827366 and INVC_BATCH_NBR = 2809526, the following number of rows are available in the staging tables: - 1 row in the O1 table - 2 rows in the O2 table (1 for each reason code: Q and D) - 2 rows in the O3 table (1 for each carton nbr: FF0024822654 and FF0024822655) - 2 rows in the O4 table (1 for each carton nbr: FF0024822654 and FF0024822655) Since in the integration layer, we are connecting the files to perform the payload to inject to MFCS, based in the PKT_CTRL_NBR, INVC_BATCH_NBR and SIZE_DESC in this case the query will do a Cartesian product, because for the same KEY finds different reason codes (repeating for each O2 row, the items/size_desc in the O4 file). Is this a valid case scenario? If so, this key is not enough to uniquely identify the reason_code/carton/item combination and therefore, the quantities won't match. [3:58 PM] Jamal Wehbe Antonio Romualdo (Guest) for the RTV with same SKU and different reason code yes its a valid scenario (1 liked)?[3:58 PM] Jamal Wehbe Fahad Gulzar ?[4:00 PM] Jamal Wehbe Antonio Romualdo (Guest) shall we open a defect "RTV one item with Different reason codes" [4:34 PM] Antonio Romualdo (Guest) Jamal Wehbe, yes a defect can be created for this issue, however the actual integration logic looks to the fields mentioned before, to perform the link between the O files and rows. In this case, how can we know (in a 1 to 1 relationship) from the O2 file which quantities belong to one reason code and which belong to the other reason code, since in this case, it's the same sku id? ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 26/07/2021: @Anu, @Jamal can you please review AntonioÂ´s question and provide feedback ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/27/2021: David - defect is for traceability. currently the link between O2 and O4 as Antonio stated is made by matching PKT_CTRL_NBR, INVC_BATCH_NBR and SIZE_DESC. Will manhattan send a PKT_CTRL_NBR, INVC_BATCH_NBR varying in case there are multiple reason codes for same item? Jamal - it's one rtv why will have different batch numbers Antonio - let me give a practical example: We received the Invoice Files for the pkt_ctrl_nbr = 013827366, invc_batch_nbr = 2809526 and size_desc = 000144685 (O1065645, O2065645, O3065645 and O4065645). In the O2065645 file, we have the following rows: In the O4065645 file, we have the following rows: For the same SIZE_DESC (000144685), PKT_CTRL_NBR (013827366) and INVC_BATCH_NBR (2809526) we have 2 reason codes in the O2 file (reason codes D and Q). In this case, how do we know, in the O4065645 file, which BUNDLES_PAKD belong to the reason code D and which BUNDLES_PAKD belong to the reason code Q for this SIZE_DESC/SKU? Jamal - what about pkt_seq_nbr position 64 under O2 and position 114 under O4, i think by considering the PKT_SEQ_NBR u can identify which reason for which line ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 27/07/2021: Antonio Romualdo added a comment Manhattan team will confirm if: the O4 file will always have the field PKT_SEQ_NBR (position 114-118) fulfilled in order to link to the O2 PKT_SEQ_NBR field (position 64-68) this change can be added to the CR list Antonio Romualdo (Guest) Jamal Wehbe, thank you for your reply. Can we add this to the CR list? Just for making it clear, the field PKT_SEQ_NBR from the O2 (position 64-68) can be linked to the field PKT_SEQ_NBR from the O4 file (position 114-118), since this field will always be fulfilled in both files? Jamal Wehbe Antonio Romualdo (Guest) for O4 file we need to double check with MA Prabhakaran Suruli please drop and email to Simon ASAP to confirm that under both O2 and O4 file pkt_seq_nbr will never be null Qadri Mohd Hussain PrtScr capture_2 ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/28/2021: Ticket raised with MA ________________________________________ Jamal Wehbe <panda_jamalw>, 7/28/2021: @Antonio - responce from MA Ideally, this field is populated from following field in PKT_DTL table - which is already set to NOT NULL. Therefore, we will not have any data sent in the O2 & O4 files with NULL in PKT_SEQ_NBR field. The value we have in the document might have been a typo overseen during preparation. Anyway, we will communicate this to Manhattan to correct the document and resend it accordingly. ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 28/07/2021: Antonio Romualdo added a comment Ok, Jamal, thank you for your input. Should this change be added to the CR list? Thank you. ________________________________________ Jamal Wehbe <panda_jamalw>, 7/29/2021: why its considered as a CR? we identified an issue here in case of we are sending multiple reason codes for the same SKU, please check with Fahad on this regard ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 29/07/2021: Antonio Romualdo added a comment Jamal, the interface was developed according to the agreed design and the fields you suggested to link O2 and O4 are not being considered at the moment. This will cause changes into our staging tables and code and this needs to be planned accordingly. Thank you. ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 7/29/2021: As discssed in triage, assigning to Oracle ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 29/07/2021: Antonio Romualdo added a comment This issue has been detected when integration layer received Invoice Files where the O2 file (that insert records into STG_MANHT_PICKTICKET_DTL_IN) had 2 rows with different reason codes for the same item/SKU 1 row for the SKU 144685 with reason code D 1 row for the SKU 144685 with reason code Q As per agreed design, the integration layer is linking the Invoice Files (O1, O2, O3, O4) with the field PKT_CTRL_NBR (present in all the invoice files) and in this case, when linking the O2 file (where different reason codes for the same item are present) with the O4 file (where the item and its quantities and weights are present), a cartesian product is done, since there's no direct connection between the O2 and O4 file that allows to match the specific reason code with the quantities/weights in the O4 file. In this issue, the following values were in the O2 and O4 files: O2 O4 After processing the data, the final result is presented below: INTG_RTV_DETAIL A suggestion made by Manhattan team is to use the field PKT_SEQ_NBR from the O2 file (position 64-68) to link with the field PKT_SEQ_NBR from the O4 file (position 114-118) in order to stablish a link between the reason code(s) and the quantities/weights. Since this field (PKT_SEQ_NBR) is not currently being integrated into our staging tables, an CR needs to be putted in place for changing the tables, update OICs and db package to incorporate and to use this field Tiago Marques added a comment Hi Ricardo Silva, The suggestion by Manhattan team to use the field PKT_SEQ_NBR to resolve the issue is not possible without several changes, because the field is not being stored in the database to apply the recommended logic. Please review CV027 last version, and the field will not be found. The issue was classified as a change request. ________________________________________ Jamal Wehbe <panda_jamalw>, 7/30/2021: SOURCE TYPE NAME FIELD TYPE FIELD LENGTH MANDATORY COMMENTS Flat File Field PKT_SEQ_NBR NUMBER 5 Yes PickticketLineNbr Flat File Field PKT_SEQ_NBR NUMBER(5) 5 No PickticketLineNbr ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 8/1/2021: @Fahad - Need you inputs on this ________________________________________ Fahad Gulzar <panda_fahadg>, 01/08/2021: @Jamal Wehbe, @Qadri Mohd Hussain, Can you call for a meeting with Khadeer included and explain the issue. @Antonio Romualdo (Guest), @David Ferreira (Guest), Will the inclusion of pickticket sequence number and linking O2 and O4 on that in addition to pickticket control number and invocie batch number solve this issue? @Jamal Wehbe, @Prabhakaran Suruli, @Qadri Mohd Hussain, Will this happen when we are creating RTVs from Manhattan or can this also happen if RTVs are initiated from RMFCS? Can this behavior be restricted by system to not have multiple reasons for the same SKU in the same pickticket? If this is deemed as CR then this will not be ready in time for GO LIVE and we will need to restrict this scenario somehow. Can you check with MA on this? ________________________________________ Jamal Wehbe <panda_jamalw>, 8/2/2021: for the RTV issued from RMFCS for the same item with different reason codes the issue we faced @Anu please may u arrange a call with David, Antoni and Fahad to disucss further mean while for going live the transaction for creating and RTV in WMS will be disabled till Return flag CR and multiple reason codes issue get fixed ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 8/2/2021: Hi Fahad, As requested in triage, Can you help to explain the criticality of the business scenario of RTV having different reason code for ORC to take this CR ________________________________________ Anudevi.ThesinguRaja <cts_anudevi>, 8/4/2021: Fahad - Until that CR is delivered we will not use RTV initiation from Manhattan JAmal will remove access from all DC members to create RTVs from Manhattan Once CR is delivered we will give access to start using from Manhattan. ChangeRequest ________________________________________ Jamal Wehbe <panda_jamalw>, 8/4/2021: we can control and prevent RTV from WMS to RMFCS but what about the RTVs coming from RMFCS how to prevent creating and RTV for the same item with different codes ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 05/08/2021: Fahad Gulzar: Simao Rio (Guest), Manon Brard (Guest), Under same RTV created in RMFCS can the same SKU be repeated with two different reason codes? If so can we please test this scenario and see if the same doubling is being experienced. IF not then we are safe to use RTVS initiated from RMFCS until the CR for RTVs from MAnhattan is delivered after R2. Fahad Gulzar: Rajesh Deshmukh (Consultant), Can we please test this scenario above? Manon Brard : Fahad Gulzar yes in RMFCS we can create RTV with same item and 2 different codes, RTV 615000 is created for wh 993 with item 100214077 twice if you want to retest David Ferreira : Hi Fahad Gulzar the issue is always in the part that Manhattan ships the RTV and sends the invoice files with two lines (due to the different reasons) having the same item. So if an RTV is initiated in MFCS and someone puts the same item being returned with different reasons then end result when Manhattan performs the return will be the same issue of duplicated qty. ________________________________________ Ricardo Filipe da Silva <oracle_rsilva>, 05/08/2021: It was agreed in the triage meeting (05/08) that by business process we cannot have a repeated SKU in an RTV, until we have the CR implemented in the environment. | 706065 | 2022-01-04 08:29 |  |  | 309:19 | SLA Violated | 2021-10-21 11:19 | FALSE |  | Integration Vendor Support Group | Low | 1 |  | 37015 | David Machado |  |  | CR#63 / SR 3-27670858661 | Luis Martins |  |  | 12 | Low | Agreed To be delivered after go-live |  | Savola Tower |  |  |  |  | integrationpt@panda.com.sa |  | Integration Project Team |  |  |  | RIB Vendor Support | Phone | Ready for Deployment â€“ Non Prod |  |  | RMS | PGL - Panda Issue 1497 - WMS RTV 1 Item different reason code [CR #63] |  |  |  | CR #63,3-27670858661 - 22523831 | Incident | 0:00 |  | 2021-12-28 13:29 | Low |  |  | All Locations
|  | Retail | Enhancement Related |  | 2021-09-02 21:11 |  |  | Information Technology | Pre Go Live defect 1538 HPQC raised by: oracle_manonb MyService raised by: Ricardo Silva Teste stage: R2_PostUAT Following CR 1422 to select Unit quantity if SKU_ATTRIB_5 = N , another issue was raised because Manhattan can send opposite adjustment type (Substract and Add) in both field (Weight adjustment type and unit adjustment type). Manhattan requests that the Adjustment type is selected depending on the SKU_ATTRIB_5 IF SKU_ATTRIB_5 = N, select the UNIT_ADJ_TYPE IF SKU_ATTRIB_5 = K, select the WEIGTHT_ADJ_TYPE Manhattan team to confirm if there are any other specific scenarios to consid Ricardo Filipe da Silva <oracle_rsilva>, 24/08/2021: Manon Brard: Jamal Wehbe, I created the defect 1538, can you please enrich it with every possibility in Manhattan ? Such as, can the adj type be empty
|  | Retail | Application Performance |  | 2021-09-08 15:33 |  |  | Information Technology | ReSA UI Issue: The SAIMPTLOGI batch is performing 1st rounding and then summing up while the UI is first summing the values up and then rounding. Analysis needs to be completed. | 709566 | 2021-09-13 12:33 |  |  | 0:28 | Within SLA | 2021-09-08 16:01 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | Medium | 1 |  | 33853 | Svyatoslav Tezin |  |  | 3-26956624811 | Rui Machado | No status changes | No status changes | 29 | Medium | SR was opened to Oracle. |  | Savola Tower |  |  |  |  | logichypercare@panda.com.sa |  | Logic Hypercare |  |  |  | RMFCS Retail Finance and Pricing Vendor Support | MS Teams | Pending With Vendor |  |  | RMS | ReSA Calculation of Item Total, Discount Total, Transaction Totals is not fully aligned with the SAIMPTLOGI batch |  |  |  | 3-26956624811 - 22438127 | Incident | 0:00 |  | 2021-12-28 13:36 | Medium |  |  | My Team
|  | Retail | Application Performance |  | 2021-09-09 18:17 |  |  | Information Technology | Hi Team, Logging this issue on behalf of Deal Creation using BoT tool. The issue was already discussed with Mr. Sergio(ORC)/Mr. Rajesh and logging the defect. Steps to re-create 1. Prepare the Deal Spreadsheet (VFP) 2. Load the file into the particular path. 3. Run multiple BOT to load the data from the file into RMFCS 4. After entering few lines(Appx: 15 VFP components) system hangs and shows an attached error message. | 710215 | 2021-09-09 22:17 |  |  | 0:00 | Within SLA | 2021-09-10 12:52 | FALSE |  | RMFCS Vendor Support | High | 1 |  | 34300 |  |  |  | SR 3-27038112481 | Carlos da Costa | Hello Ivan, Deal mass upload is currently not supported. As communicated previously, an enhancement has been raised with product development to consider it for future releases. Regards Shwetha | Hello Ivan, Deal mass upload is currently not supported. As communicated previously, an enhancement has been raised with product development to consider it for future releases. Regards Shwetha | 41 | Urgent | Waiting Oracle Feedback Oracle Team needs to schedule a call to understand the reffered steps in order to get a error. can you provide a number and a schedule (timezone) to share with Oracle |  | Savola Tower |  |  |  |  | gpappnnan@panda.com.sa | 9986739790 | Gunasekharan Pappnnan |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  | RMS | RMFCS Performance Issue - BoT-Deals |  |  |  | 3-27038112481 - 22438127 | Incident | 0:00 |  | 2021-12-28 14:06 | High |  |  | My Team
|  | Retail |  |  | 2021-09-12 09:29 |  |  |  | Comparing the files received under staging folder and found that not all are copied to MFCS_INBOUND_FILES folder. Attached snapshot for further reference | 710925 | 2021-09-13 08:29 |  |  | 0:19 | Within SLA | 2021-09-12 09:48 | FALSE |  | Integration Vendor Support Group | High | 1 |  | 34150 |  |  |  | 3-27924571271 | Luis Martins |  |  | 81 | High |  |  | Savola Tower |  |  |  |  | jwehbe@panda.com.sa |  | Jamal Ali Wehbe |  |  |  | RIB Vendor Support | Phone | Pending With Vendor |  |  | RMS | Manhattan-Missing files under MFCS_INBOUND_FILES |  |  |  |  | Incident | 0:00 |  | 2021-12-30 20:08 | Medium |  |  | All Locations
|  | Retail |  |  | 2021-09-12 11:17 |  |  | Finance | Reported by Ram. We unable to continue invoice creation in below screen after clicking 'Save and Add another' option. it moves out when i click save and Add another option in IMCS. | 711008 | 2021-09-16 15:17 |  |  | 0:08 | Within SLA | 2021-09-12 11:25 | FALSE |  | RMFCS Vendor Support | High | 1 |  | 35454 | John Jones |  |  | SR 3-27240525201 | Carlos Pinho | Oracle Services Management added a public note 29 minutes ago (Mon, 3 Jan at 12:28) Notified to : gpappannan@panda.com.sa Hi Guna, Oracle has asked if you are still getting this error after the update. Can you please retest and let me know? Thanks | JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi Rene, Please see below the customer update after tested: "Ram Lamsal added a public note 21 hours ago (Mon, 3 Jan at 14:11) Dear ORC Team, Still, this issue has not been resolved. Regards," Best Regards, José Aguiar | 30 | Low | New update on the SR, Oracle gave the same suggestion, applying the Patch 19.2.009. Can it be? What is the downtime to do that? |  | Savola Tower |  |  |  |  | rlasmal@panda.com.sa |  | Ram Lamsal |  |  |  | No Agent | Phone | Pending With Vendor |  |  | REIMCS | ReIM - unable to continue invoice creation after clicking 'Save and Add another' |  |  |  |  | Incident | 0:00 |  | 2021-12-30 18:18 | Medium |  |  | My Team
|  | Retail |  |  | 2021-09-14 17:57 |  |  | Information Technology | Currently in RMFCS, Catch Weight Items (with CW Ind = Y) can be created/approved without the Case Weight Dimensions defined. Moreover, when adding a new parent supplier to such items, it is also not mandatory to define Case Weight Dimensions. This definition needs to be ensured by Business Process. However, if the business process fails, these items will have data issues thrown by several processes: - we have detected Pricing batches failing (PriceEventExecution) if price changes are created for these items - we have detected ASNout messages failing for these items For this reason, an SR should be logged in MOS for Oracle product team/DEV to take action and fix/enhance this scenario. | 712433 | 2021-09-21 12:00 |  |  | 66:47 | SLA Violated | 2021-09-26 11:47 | FALSE |  | RMFCS Vendor Support | Medium | 1 |  | 34586 |  |  |  | SR 3-27167309171 | Vitor Goncalves | No status changes | No status changes | 28 | Low |  |  | Savola Tower |  |  |  |  | rmfcsptassets@panda.com.sa |  | RMFCS Project Team |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  | RMS | RMFCS - CW items - Case Weight definition is not mandatory |  |  |  | 3-27167309171 - 22438127 | Incident | 0:00 |  | 2021-12-28 14:19 | Medium |  |  | My Team
|  | Supply Chain Oracle Procurement | Functional Issue |  | 2021-09-15 14:21 |  |  | Information Technology | 1. SABS initiate the transfer order request 2. Integration Layer generates the transfer order in RMFCS 3. SABS order reference no is populated in the comments field in RMFCS 4. Expectation is to populate in the TSFHEAD_CFA_EXT reference field ( similar to ORDHEAD_CFA_EXT) Data Point: TSF NO: 19016218
|  | Integration Layer | Functional Issue |  | 2021-09-21 15:19 |  |  | Information Technology | Hi Carlos, There is only one line item in the transfer in RMFCS but while coming to GMDH through ID 177, its creating 3 lines by different expected arrival date. This is not letting orders to be generated in GMDH due to huge open order quantity. Please see the screen shots below. This needs urgent attention and fix. RMFCS screen one line item Received 3 lines in file. Created 3 lines in GMDH database Please see attachment There are many such cases and below is another example. Please check select * from tsfdetail where tsf_no = 19130653 and item = 100147682 select * from tsfhead where tsf_no = 19130653 select * from shipment where shipment in (select shipment from shipsku where distro_no = 19130653 and item = 100147682) | 715526 | 2021-09-22 14:19 |  |  | 0:38 | SLA Violated | 2021-09-21 15:57 | FALSE |  | Integration Vendor Support Group | High | 1 |  | 37041 |  |  |  | CR #82 / 3-27734442591 | Luis Martins |  |  | 30 | High | Waiting for Atif feedback |  | Savola Tower |  |  |  |  | atkhan@panda.com.sa |  | Atif Khan |  |  |  | RIB Vendor Support | Phone | Ready for Deployment â€“ Non Prod |  |  | POM | ID 177 Transfer / item came with mulitple records to GMDH interface. |  |  |  | CR #82,3-27734442591 - 22523831 | Incident | 0:00 |  | 2021-12-28 14:21 | High |  |  | All Locations
|  | Retail |  |  | 2021-09-27 12:58 |  |  | Supply Chain | Dear Team, Pls. your support to check and fix the variance that we have between Manhattan SOH and RMFCS. Kindly open the attached file for more details. Manhattan was capture in SCI report and RMFCS was capture in SOH + Transactional report in Oracle. | 717650 | 2021-09-28 11:58 |  |  | 3:14 | Within SLA | 2021-09-27 16:12 | FALSE |  | RMFCS Vendor Support | High | 1 |  | 34689 |  |  |  |  | Luis Martins |  |  | 119 | High |  |  | Distribution Centre |  |  |  |  | rgaloy@panda.com.sa | 966 540 28 7112 | Romar Cabinte Galoy |  |  |  | RMFCS Vendor Support | Portal | Open | DC991 (KAEC) |  | REIMCS | Manhattan and RMFCS SOH mismatch |  |  |  |  | Incident | 0:00 |  | 2021-12-27 16:10 | High |  |  | My Team
|  | Retail | Functional Issue |  | 2021-09-27 15:53 |  |  | Supply Chain | Dear Mousumi, we Extracted a report from ILR and it was 68MB File, If we open the file, than the file is corrupted. Please support to fix the issue | 717777 | 2021-09-30 12:53 |  |  | 1:54 | Within SLA | 2021-09-27 17:47 | FALSE |  | RMFCS Vendor Support | Medium | 1 |  | 37635 |  |  |  |  | Carlos Costa |  |  | 19 | Medium | We are not concerned with it Please assign to Oracle ILR App Support |  | Savola Tower |  |  |  |  | skatpadi@panda.com.sa | 556763742 | Sadaqath Katpadi |  |  |  | RMFCS Vendor Support | Portal | Open |  |  | RMS | File corrupted above 68 MB file |  |  |  |  | Incident | 0:00 |  | 2021-12-27 10:13 | Medium |  |  | All Locations
|  | Financials Oracle Receivables |  |  | 2021-09-30 11:15 |  |  | Finance | We have issue with all receipts which have decimal qty. As you know in RMFCS there are 4 digit after decimal and in IMCS there are 3 digit after decimal in qty. Due to this variance system always show qty discrepancy in IMCS. We try to resolve these invoice manually but system not resolving. PO# 52068982. | 719205 | 2021-09-30 15:15 |  |  | 5:45 | SLA Violated | 2021-09-30 20:52 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | High | 6 |  | 34840 |  |  |  | SR 3-27241839551 | Antonio da Silva | SVYATOSLAV.TEZIN@ORACLE.COM - 4 mins ago [Update from Customer] Hi all, To align, on the " SR 3-27665894791 : Cannot match invoices due to Application Error" we are asking to delete the below invoices so that Ram can create those and match from scratch. Invoice ¦ Document Date ¦ Order No. ¦ Vendor ¦ Location ¦ Total Cost 396505763 ¦ 09/19/21 ¦ 52177653 ¦ 3612 ¦ 85 ¦ 11,930.45 214130000318 ¦ 09/19/21 ¦ 52069360 ¦ 3916 ¦ 78 ¦ 295.32 M90072835 ¦ 10/07/21 ¦ 52346887 ¦ 3498 ¦ 105 ¦ 2,051.90 21731 ¦ 09/04/21 ¦ 51996976 ¦ 9434 ¦ 265 ¦ 47,169.90 0965 ¦ 09/06/21 ¦ 52002292 ¦ 10058 ¦ 265 ¦ 45,841.38 1458 ¦ 09/07/21 ¦ 52009005 ¦ 9689 ¦ 265 ¦ 10,895.65 3408 ¦ 09/04/21 ¦ 51996974 ¦ 9755 ¦ 265 ¦ 46,235.10 Ivan and RC tem, please note that the list has been updated by Ram and re-shared in Panda teams. Regards Slava | Oracle Support - 18+ hours ago [Notes] We have received your request. We are looking into it and will keep you updated on the progress. SVYATOSLAV.TEZIN@ORACLE.COM - 22+ hours ago [Update from Customer] Hi all, To align, on the " SR 3-27665894791 : Cannot match invoices due to Application Error" we are asking to delete the below invoices so that Ram can create those and match from scratch. Invoice ¦ Document Date ¦ Order No. ¦ Vendor ¦ Location ¦ Total Cost 396505763 ¦ 09/19/21 ¦ 52177653 ¦ 3612 ¦ 85 ¦ 11,930.45 214130000318 ¦ 09/19/21 ¦ 52069360 ¦ 3916 ¦ 78 ¦ 295.32 M90072835 ¦ 10/07/21 ¦ 52346887 ¦ 3498 ¦ 105 ¦ 2,051.90 21731 ¦ 09/04/21 ¦ 51996976 ¦ 9434 ¦ 265 ¦ 47,169.90 0965 ¦ 09/06/21 ¦ 52002292 ¦ 10058 ¦ 265 ¦ 45,841.38 1458 ¦ 09/07/21 ¦ 52009005 ¦ 9689 ¦ 265 ¦ 10,895.65 3408 ¦ 09/04/21 ¦ 51996974 ¦ 9755 ¦ 265 ¦ 46,235.10 Ivan and RC tem, please note that the list has been updated by Ram and re-shared in Panda teams. Regards Slava | 67 | Urgent | Hi Ram, can you answer to this: What is right receipt or invoice? What is the resolution option that you was chosen, for each of the rows? |  | Savola Tower |  |  |  |  | rlasmal@panda.com.sa |  | Ram Lamsal |  |  |  | RMFCS Retail Finance and Pricing Vendor Support | Phone | Pending With Vendor |  |  |  | Unable to resolve invoices due to qty Decimal issue |  |  |  | 3-27241839551 - 22438127 | Incident | 0:00 |  | 2021-12-28 14:37 | High |  |  | My Team
|  | Retail |  |  | 2021-10-06 04:04 |  |  | Marketing | Hi Team, Please look at the delete Cost event option as it is not working from our side. We are trying to delete an event as it it blocking the mass upload that we are doing. we need to delete the records initially recorded in the staging tables before we can proceed, we are targeting to delete Cost Change with Worksheet and Submitted statuses under user ID 20963 which is apparently not working. Thanks, | 721019 | 2021-10-10 14:00 |  |  | 2:09 | SLA Violated | 2021-10-06 10:09 | FALSE |  | RMFCS Vendor Support | Medium | 12 |  | 35030 |  |  |  | SR 3-27369964201 | Carlos Costa | No status changes Mantis foi fechado . | No status changes Mantis foi fechado . | 36 | Medium | Hi Percival Santos, Can you please share a step by step on how do do this action? Did you get any error? If so please share the print. Thank you. Best regards JosÃ© Aguiar |  | Savola Tower |  |  |  |  | pbsantos@panda.com.sa |  | Percival Santos |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  | RMS | Unable to delete Cost Change with Worksheet and Submitted statuses under user ID 20963 |  |  |  | 3-27369964201 - 22438127,RMFCS19.2.011 | Incident | 0:00 |  | 2021-12-28 14:44 | Medium |  |  | All Locations
|  | Financials Oracle Payables | Functional Issue |  | 2021-10-06 14:12 |  |  | Information Technology | Problem Description --------------------------------------------------- Steps to re-create 1. Create Merchandise Fixed Deal 2. Merchandise Hierarchy Add department 3. In location, all locations 4. Nightly batch which generates deal gets failed due to closed store Expected Result: when businesses select all stores, the system will consider only the active store not closed stores. Why the system is including closed/inactive stores. | 721322 | 2021-10-11 11:12 |  |  | 16:26 | SLA Violated | 2021-10-07 06:38 | FALSE |  | RMFCS Vendor Support | Medium | 1 |  | 35342 |  |  |  | SR 3-27268145391 | Vitor Goncalves | No status changes SR fechado pela oracle incidente passado ao cliente MOM . | No status changes SR fechado pela oracle incidente passado ao cliente MOM . | 18 | Medium | Oracle asked for screenshots of each step, can you provide this please? Can you add more detail, to update the SR afer the OWC. Thank you |  | Savola Tower |  |  |  |  | gpappannan@panda.com.sa | 9986739790 | Gunasekaran Pappannan |  |  |  | RMFCS Vendor Support | Chat | Pending With Vendor |  |  |  | Fixed Deal- System allows to create fixed deal for all stores including the closed store |  |  |  | 3-27268145391 - 22438127 | Incident | 0:00 |  | 2021-12-29 13:28 | Medium |  |  | All Locations
|  | Retail |  |  | 2021-10-07 09:28 |  |  | Finance | Hi Team, Need your support on this: System allows to create Duplicate Debit Memo Document Thanks, | 721609 | 2021-11-22 12:47 |  |  | 6:00 | SLA Violated | 2021-10-07 15:28 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | Medium | 1 |  | 35595 |  |  |  | SR 3-27305928211 | Luis Martins | No status changes | No status changes | 28 | Medium | Still no update on 18 Nov |  | Savola Tower |  |  |  |  | rlasmal@panda.com.sa |  | Ram Lamsal |  |  |  | No Agent | Phone | Pending With Vendor |  |  | REIMCS | Duplicate Debit Memo |  |  |  | 3-27305928211 - 22438127,RMFCS19.2.011 | Incident | 0:00 |  | 2021-12-28 14:47 | Low |  |  | All Locations
|  | Retail |  |  | 2021-10-07 09:35 |  |  | Finance | Hi Team, Qty Decimal places are showing two decimals at header level and line level it is showing 3 decimal places even though setup the qty decimal places to 4 decimals. Thanks, | 721615 | 2021-10-10 08:35 |  |  | 6:36 | SLA Violated | 2021-10-07 16:11 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | High | 1 |  | 35663 |  |  |  | 3-27556313061 | Antonio da Silva | No status changes | No status changes | 37 | High | Can you please see the answer from Guna and the attached screenshot? |  | Savola Tower |  |  |  |  | rlasmal@panda.com.sa |  | Ram Lamsal |  |  |  | RMFCS Retail Finance and Pricing Vendor Support | Phone | Pending With Vendor |  |  | RMS | Qty Decimal places are showing two decimals at header level and line level it is showing 3 decimal places even though setup the qty decimal places to 4 decimals. |  |  |  | 3-27556313061 - 22438127 | Incident | 0:00 |  | 2021-12-28 14:59 | High |  |  | All Locations
|  | Supplier Portal |  |  | 2021-10-14 09:23 |  |  | Information Technology | orca_email_rtv_addtoq.ksh running for long | 724330 | 2021-10-20 13:23 |  |  | 172:31 | SLA Violated | 2021-10-21 13:54 | FALSE |  | RMFCS Vendor Support | Medium | 1 |  | 36531 |  |  |  | SR 3-27732083271 | Carlos Pinho | Sr was closed and mantis Incidente pass to the cliente. |  | 36 | Low |  |  | Savola Tower |  |  |  |  | aalsaiyed@panda.com.sa |  | Amjad Saiyed |  |  |  | RMFCS Vendor Support | Phone | Pending |  |  |  | orca_email_rtv_addtoq.ksh running for long |  |  |  | 3-27732083271 - 22523831 | Service Request | 0:00 |  | 2021-12-28 18:44 | Low |  |  | All Locations
|  | Retail |  |  | 2021-10-14 15:06 |  |  | Finance | In Summary Matching screen, the receipt Qty is showing negative value Steps Re-create Navigate to Invoice Matching screen Enter PO number and click search In the search result screen , Receipt tab is showing negative Qty and Negative Value. However the qty is not nagative as per receipt When user click Summary match, it will take you to the summary match screen. In this screen, the receipt qty and reciept value is showing correctly. Please refer the below screen shot . | 724576 | 2021-10-14 19:06 |  |  | 1:54 | Within SLA | 2021-10-14 19:37 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | Medium | 1 |  | 35567 |  |  |  | SR 3-27449790531 / SR 3-27665894791 | Antonio da Silva | No status changes | No status changes | 65 | Urgent | can you please provide the 2REIM_ONLINE_MATCH_SQL from PRD environment? |  | Savola Tower |  |  |  |  | rlasmal@panda.com.sa |  | Ram Lamsal |  |  |  | RMFCS Retail Finance and Pricing Vendor Support | Phone | Pending With Vendor |  |  | REIMCS | In Summary Matching screen, the receipt Qty is showing negative value |  |  |  | 3-27449790531 - 22438127,3-27665894791 - 22438127 | Incident | 0:00 |  | 2021-12-28 15:39 | Medium |  |  | My Team
|  | Retail | Enhancement Related |  | 2021-10-14 15:43 |  |  | Supply Chain | the request came from Omara Gazzaz (MDM Team) to change the mapping for the items flowing to WMS from RMFCS current: Item_desc new requirement: Short Desc Regards | 724604 | 2021-10-21 10:43 |  |  | 76:23 | SLA Violated | 2021-10-17 20:06 | FALSE |  | Integration Vendor Support Group | Low | 1 |  | 36656 |  |  |  | CR# 91 / SR 3-27640484341 | Luis Martins |  |  | 26 | Low |  |  | Savola Tower |  |  |  |  | ogazzaz@panda.com.sa |  | Omar Gazzaz |  |  |  | RIB Vendor Support | Phone | Ready for Deployment â€“ Non Prod |  |  | RMS | Changing the Mapping of ITem desc flowing from RMFCS to WMS ID62 |  |  |  | 3-27640484341 - 22523831 | Incident | 0:00 |  | 2021-12-28 15:42 | Low |  |  | All Locations
|  | Retail |  |  | 2021-10-17 12:48 |  |  | Finance | Unable to fetch data on discrepancy review list screen. It is showing error message as shown below. | 725494 | 2021-10-21 16:48 |  |  | 24:04 | Within SLA | 2021-10-18 12:52 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | Low | 4 |  | 35667 |  |  |  | 3-27606141781 | Antonio da Silva | No status changes | No status changes | 37 | Low | issue has been resolved please check now SR 3-27462158111 was closed |  | Savola Tower |  |  |  |  | rlasmal@panda.com.sa |  | Ram Lamsal |  |  |  | RMFCS Retail Finance and Pricing Vendor Support | Phone | Pending With Vendor |  |  | REIMCS | Unable to fetch data on discrepancy review list screen. |  |  |  |  | Incident | 0:00 |  | 2021-12-29 20:08 | Low |  |  | My Team
|  | Promotion Work Flow | Functional Issue |  | 2021-10-20 20:06 |  |  | Information Technology | It has been noticed that when a Happy Hour promotion (custom Start and End time) is created in RPCS, it is not being discarded from being sent to POS by Integration Layer. Happy Hour Promotions are only supported by Genius and should not be sent to POS. This ticket is to address this scenario and make sure all HH promotions only flow to Genius, and not POS system. | 727274 | 2021-10-25 14:00 |  |  | 3:23 | SLA Violated | 2021-10-21 11:23 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | Medium | 1 |  | 35866 |  |  |  | 3-27456232001 | Vitor Goncalves | No status changes | Customer was updated; JOAO.FONTAO@ORACLE.COM - 19 mins ago [Retail] Hello Ivan To perform the test correctly, you need to follow the following steps: 1. Create promotions with the correct dates (check vdate) 2. Approve the offers 3. Run the PromotionOffer_Tx_SubProcessFlow_From_RMS_To_EXTERNAL process or wait for it to run automatically 4. Start following the steps in UT. Best Regards João Fontão Oracle Global Customer Support | 44 | Medium | Validate if BDI-PES flow job is running without issues before doing the call. Redo the test, documenting all steps and making sure the needed jogs execute successfully. |  | Savola Tower |  |  |  |  | rmfcspt@panda.com.sa |  | RMFCS Retail Finance and Pricing Project Team |  |  |  | RMFCS Retail Finance and Pricing Vendor Support | Phone | Pending With Vendor |  |  |  | Happy Hour Promotions - PES Integration Export needs to discard these offers to POS |  |  |  | 3-27456232001 - 22523831 | Incident | 0:00 |  | 2021-12-30 13:08 | Medium |  |  | All Locations
|  | Retail | Enhancement Related |  | 2021-10-21 14:29 |  |  | Business Support | Hi Team - Can you please help with "READ ONLY" role for all assets except Supplier Portal? Thank You | 727536 | 2021-10-28 09:29 |  |  | 1:38 | Within SLA | 2021-10-21 16:07 | FALSE |  | RMFCS Vendor Support | Medium | 1 |  | 35909 |  |  |  | SR 3-27493594211 | Antonio da Silva | SR was closed - As CR87 is planned to be deploy by the end of Jan22, this ticket will no longer be updated until any extra information regarding this planning. Status updated. Tks.. | SR was closed - As CR87 is planned to be deploy by the end of Jan22, this ticket will no longer be updated until any extra information regarding this planning. Status updated. Tks.. | 15 | Low | Dears - Kindly advise what needs to be done as requested by Ahmed it needs to be assign to Simao We already have the approval of Sohaib to proceed |  | Savola Tower |  |  |  |  | sohaibm@panda.com.sa |  | Sohaib Masood |  |  |  | No Agent | Phone | Ready for Deployment â€“ Non Prod |  |  | RMS | Requesting a "READ ONLY" role for all assets except Supplier Portal |  |  |  |  | Incident | 0:00 |  | 2021-12-28 15:51 | Medium |  |  | My Team
|  | Retail |  |  | 2021-11-01 06:36 |  |  | Information Technology | Error Reason: oracle.xml.parser.v2.XMLParseException
|  | Financials Oracle Receivables | Functional Issue |  | 2021-11-01 14:22 |  |  | Information Technology | Steps to follow: PO creation and approval Receive the purchase order Create an Invoice at header level (Invoice value = Receipt value). Run automatch batch The invoice status has been changed to unresolved even though the invoice cost is the same as the PO/receipt cost The user manually matches the invoice with the receipt The system displays the message "Tax compliance failed. The tax on the invoice matches the tax on the receipt. The invoice will not be matched." The item vat and invoice vat are the same. Could you look into this? Data Point: Document ID: 120118505 PO: 52484508 | 731214 | 2021-12-07 10:46 |  |  | 0:33 | Within SLA | 2021-11-01 14:56 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | High | 1 |  | 36490 |  |  |  | SR 3-27596400571 | Vitor Goncalves | No status changes | No status changes | 26 | Low | Data issue needs to be fixed by business team to continue. |  | Savola Tower |  |  |  |  | gpappannan@panda.com.sa | 9986739790 | Gunasekaran Pappannan |  |  |  | RMFCS Retail Finance and Pricing Vendor Support | Chat | Pending With Vendor |  |  |  | User Unable to Match the Invoice with Receipt - Shows Tax Discrepancy |  |  |  | 3-27596400571 - 22438127 | Incident | 0:00 |  | 2021-12-28 15:58 | High |  |  | All Locations
|  | Retail | Reporting Issue |  | 2021-11-02 17:38 |  |  | Information Technology | ASNInCre messages fails due to container already exist is ASN. | 731714 | 2021-12-09 14:00 |  |  | 0:00 | Within SLA | 2021-11-02 18:06 | FALSE |  | SIM Vendor Support Group | Medium | 1 |  | 37992 |  |  |  | SR 3-27575486871 & SR 3-27584002988 | Carlos Pinho | No status changes | No status changes | 24 | Medium |  |  | Savola Tower |  |  |  |  | ssunder@panda.com.sa | 554897157 | Shyam Sunder |  |  |  | Oracle Services Management | Phone | Pending With Vendor |  |  | Oracle SIM Application | Container ID: xxxxxxx already exist for ASN: yyyyyy |  |  |  | 3-27575486871 - 22523831,3-27584002988 - 20388948 | Incident | 0:00 |  | 2021-12-28 16:02 | Medium |  |  | All Locations
|  | Supply Chain Oracle Inventory | Functional Issue |  | 2021-11-11 10:08 |  |  | Information Technology | Hi Guna, Can you please check the attached POs are old and still appearing as open.? These open orders are impacting GMDH ordering. I checked in RMFCS they are still in A status and having open order quantities even after long NBD. select * from ordhead where order_no in ( 52062432,52136202,52206824,52206827,52282980,52568709)
|  | Supply Chain Oracle Procurement |  |  | 2021-11-15 10:50 |  |  | Supply Chain | Item Short Description Change in Item is not cascaded to Item Location Level | 735830 | 2021-11-17 16:50 |  |  | 0:03 | Within SLA | 2021-11-15 10:53 | FALSE |  | RMFCS Vendor Support | Low | 1 |  | 36871 |  |  |  | SR 3-27696704841 | Carlos Costa | No status changes | No status changes | 35 | Medium | The SR has been updated and Oracle is asking the following question: So to confirm, the issue is with the Item induction, not the UI, and the issue is still present when using a spreadsheet with the size in the item description? Apologies for asking again, just need to confirm before I go back to Development. Can you please give us the feedback requested by Oracle? |  | Savola Tower |  |  |  |  | mraza@panda.com.sa |  | Mohd Raza |  |  |  | RMFCS Vendor Support | Portal | Pending |  |  |  | Item Short Description Change in Item is not cascaded to Item Location Level |  |  |  |  | Service Request | 0:00 |  | 2021-12-28 16:10 | Low |  |  | Only me
|  | Financials Oracle Payables | Functional Issue |  | 2021-11-15 16:15 |  |  | Information Technology | For incorrect VAT item invoices, as per the agreed process, the business user generates a debit memo cost with the Non-Merchandise Code "VATDISPUTE" reason code and charges the discrepancy back to the supplier. The document is in worksheet status instead of being approved when the Debitmemo cost is created with a non-merchandise code. Please refer to the below document( Debit Memo cost) which is created in worksheet status. We would like to understand why it is created in a worksheet instead of approved. | 736045 | 2021-11-15 20:15 |  |  | 3:03 | SLA Violated | 2021-11-16 10:18 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | High | 1 |  | 36927 |  |  |  | SR 3-27711611481 | Carlos Pinho | No status changes | No status changes | 28 | Urgent | SR 3-27711611481 |  | Savola Tower |  |  |  |  | gpappannan@panda.com.sa | 9986739790 | Gunasekaran Pappannan |  |  |  | RMFCS Retail Finance and Pricing Vendor Support | Phone | Pending With Vendor |  |  |  | Manually Created Debit Memo Cost for Non-Merchandise code shows in the "Woksheet" status |  |  |  | 3-27711611481 - 22438127 | Incident | 0:00 |  | 2021-12-28 14:10 | High |  |  | All Locations
|  | Supply Chain Oracle Procurement | Functional Issue |  | 2021-11-16 16:28 |  |  | Information Technology | Purchase order receipts of information are struck in the integration layer As the receipt pix confirmation is sent before the shipment and appointment are closed in RMFCS,Hence failed in integration layer. Refer the screen shot below for the failed carton details. Purchase order No: 52530146 Item: 3900305 Receipt Qty : 960 in Manhattan Receipt Qty is integrated RMFCS only 240. All failed in the integration layer. | 736491 | 2021-11-17 15:28 |  | 2021-12-02 | 0:32 | Within SLA | 2021-11-16 18:49 | FALSE |  | Integration Vendor Support Group | High | 1 |  | 36936 |  |  |  | 3-27735493111 | Ray Milliati |  |  | 37 | High |  |  | Savola Tower |  |  |  |  | gpappannan@panda.com.sa | 9986739790 | Gunasekaran Pappannan |  |  |  | RIB Vendor Support | Phone | Ready for Deployment â€“ Non Prod |  |  |  | PO Receipt Information is not interfaced from Manhattan to RMFCS |  |  |  |  | Incident | 0:00 |  | 2022-01-02 14:03 | High |  |  | All Locations
|  | Retail | Environment Issue |  | 2021-11-22 10:58 |  |  | Information Technology | Hi Simao - We are having the IT auditing and they have a question about the cloud patch deployment. I just wanted to check, whenever the cloud deployment happens does the oracle has any kind of logging which we can get and share to auditor as per their requirement. Or cloud team does have but not share to customer. Regards, Junaid Alam. | 738440 | 2021-11-23 14:29 |  |  | 0:13 | Within SLA | 2021-11-22 11:10 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | Medium | 1 |  | 37134 |  |  |  |  | Rui Machado |  |  | 7 | High |  |  | Savola Tower |  |  |  |  | jalam@panda.com.sa | 509375974 | Junaid Alam |  |  |  | RMFCS Retail Finance and Pricing Vendor Support | Portal | Pending With Vendor |  |  | RMS | Cloud Patch deployment log |  |  |  |  | Incident | 0:00 |  | 2021-12-10 18:51 | High |  |  | My Team
|  | Retail |  |  | 2021-11-23 14:54 |  |  | Supply Chain - DC | Dear Team, may we request to modify or arrange the Oracle PO SKU in sequence. it will help us to find easily the SKUs if it is in sequence or arranged in order. Thank you | 738970 | 2021-11-30 09:54 |  |  | 0:29 | Within SLA | 2021-11-23 15:22 | FALSE |  | RMFCS Vendor Support | Low | 1 |  | 38238 |  |  |  | 3-27999104161 | Carlos Costa | No status changes | No status changes | 16 | Low |  |  | Distribution Centre |  |  |  |  | dcitl@panda.com.sa | 552094486 | DC Inbound Ambient TL |  |  |  | RMFCS Vendor Support | Portal | Pending With Vendor | DC993 |  | REIMCS | to arrange the SKU in sequence in PO (Oracle) |  |  |  | 3-27999104161-22438127 | Incident | 0:00 |  | 2021-12-28 16:15 | Low |  |  | My Team
|  | Supply Chain Oracle Inventory | Functional Issue |  | 2021-11-24 10:00 |  |  | Information Technology | Hi Jahanaz, the ILR is updating the pickup lead time in repl_item_loc and for most of DSD items, its updated as 0. Saleh said they are updating is with value and not sure why its coming as 0. GMDH uses this pickup lead time as leadtime. Can you please check this urgently and update me? select * from repl_item_loc a where pickup_lead_time = 0 and exists (select 1 from item_loc b where b.source_method ='S' and a.item = b.item and b.loc = a.location and b.status ='A')
|  | Retail | Enhancement Related |  | 2021-11-24 15:54 |  |  | Information Technology | In item_supp_country_loc table cost is showing with 4 decimal place whereas in item supplier country location screen of RMFCS showing with 3 decimal place. Need to increase up to 4 to match cost value in screen with database table. Example is provided through attached file. | 739380 | 2021-12-01 10:54 |  |  | 7:18 | SLA Violated | 2021-11-25 14:13 | FALSE |  | RMFCS Vendor Support | Medium | 1 |  | 37299 |  |  |  | SR 3-27806208921 | Carlos Costa | No status changes | No status changes | 23 | Low | Waiting for client feedback. |  | Savola Tower |  |  |  |  | auddin@panda.com.sa |  | Ayen Uddin |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  | RMS | Cost showing in RMFCS Item supplier country screen with 3 decimal place need to increase up to 4 decimal. |  |  |  | SR 3-27806208921-22438127 | Incident | 0:00 |  | 2021-12-28 16:28 | Low |  |  | All Locations
|  | Retail | Functional Issue |  | 2021-11-25 14:14 |  |  | Information Technology | in RMFCs, when using the UI to create a new Catch Weight Item, it has been noticed that the Sale Type field is not validating if the Standard UOM is accordingly set up. For example, we are able to create items with Sale Type = Variable Weight Each and with a MASS Standard UOM (KG). We are also able to create Items with Sale type = Loose Weight and with Standard UOM = EA. It was also noticed that there is a field validation warning when the Sale Type = Variable Weight Each and we try to change the Standard UOM to a MASS UOM, but then Sale Type is not updated to Loose Weight. These screen validations need to be reviewed. Note that when we use the Item induction process to update these invalid items we get error messages like: "Invalid Sale Type" or "Invalid Standard UOM: Sale Type V and Standard UOM KG" | 739680 | 2021-12-02 09:14 |  |  | 0:01 | Within SLA | 2021-11-25 14:15 | FALSE |  | RMFCS Vendor Support | Medium | 1 |  | 37609 |  |  |  | 3-24301935601 | Carlos Costa | No status changes | No status changes | 13 | Low |  |  | Savola Tower |  |  |  |  | rmfcsptassets@panda.com.sa |  | RMFCS Project Team |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  | RMS | Catch Weight Sale Types are not validating Standard UOM in Item Creation |  |  |  |  | Incident | 0:00 |  | 2021-12-28 16:30 | Low |  |  | My Team
|  | Financials Oracle Receivables |  |  | 2021-11-28 17:46 |  |  | Information Technology | Steps to re-create. 1. Business user perform Receiver Cost Adjustment for an item in RMFCS 2. After the receiver cost adjustment tran code 20 C is posted in tran _data 3. Tran Code 70 C also posted in tran _data 3. However WAC is not re-calculated in RMFCS. Data Point: PO No: 52863171 Item:1348470 Location: 92 Adjustment Unit Cost : 13 Refer to attached tran_data Posting Note: This issue needs to be addressed on priority as it is nearing month closing and also receipt which impact incorrect WAC calculation. | 740551 | 2021-12-29 16:18 |  |  | 0:00 | Within SLA | 2021-11-28 18:15 | FALSE |  | RMFCS Vendor Support | High | 1 |  | 37506 |  |  |  | SR 3-27832605471 | Carlos Costa | No status changes: Gunasekaran Pappannan added a public note 5 days ago (Wed, 29 Dec, 2021 at 13:24) Fine, please check with them and schedule a call. Regards Guna | No status changes: Gunasekaran Pappannan added a public note 5 days ago (Wed, 29 Dec, 2021 at 13:24) Fine, please check with them and schedule a call. Regards Guna | 21 | Urgent | Opened SR 3-27832605471. |  | Savola Tower |  |  |  |  | gpappannan@panda.com.sa | 9986739790 | Gunasekaran Pappannan |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  |  | Receiver Cost Adjustment (RCA) done in RMFCS Does Not Recalculate WAC |  |  |  | SR 3-27832605471 - 22438127 | Incident | 0:00 |  | 2021-12-29 13:25 | High |  |  | All Locations
|  | Retail |  |  | 2021-11-29 08:37 |  |  | Operations | Dear IT team, Kindly be noted as we notice when we schedule CC if their is one SKU linked to multiple SKU due to PC's Pack, Outer. in Authorization system capture only the simple pack QTY and ignoring other QTY like cases or outer. Appreciate your support to fix the issue asap as it will impact on our stock accuracy. | 740623 | 2021-12-05 12:37 |  |  | 26:06 | SLA Violated | 2021-11-30 10:43 | FALSE |  | SIM Vendor Support Group | Low | 3 |  | 37640 |  |  |  | SR 3-27874541491 | Carlos Pinho | WSOBHI@PANDA.COM.SA - 21+ hours ago [Update from Customer] yes please book for a meeting as soon as Alex is available. please add my email : wsobhi@panda.com.sa Wael Sobhi Regards, | WSOBHI@PANDA.COM.SA - Sunday [Update from Customer] yes please book for a meeting as soon as Alex is available. please add my email : wsobhi@panda.com.sa Wael Sobhi Regards, | 19 | Low | Can you review the SR update |  | Savola Tower |  |  |  |  | mamahmoud@panda.com.sa | 508393228 | Mahmoud Mostafa |  |  |  | SIM Vendor Support | Portal | Pending With Vendor |  |  | Oracle SIM Data | cycle count Authorized QTY Bug |  |  |  |  | Incident | 0:00 |  | 2021-12-23 13:34 | Low |  |  | All Locations
|  | Financials Oracle Payables | Functional Issue |  | 2021-11-30 10:22 |  |  | Information Technology | After performing RCA, ReIM EDI Injector Batch Inserts Reason Code As Null For Debit Memo Cost Document- Failed in Invoice Posting Steps To Replicate: 1. Perform Receipt Cost Adjustment(RCA) in RMFCS for closed receipts from Retail Merchandising System(RMS) and adjusted cost<ORDLOC.UNIT_COST. 2.Check if record created in INVC_XREF, INVC_HEAD, INVC_DETAIL. 3. Run EDIDLINV batch 4. Run EDI_INVOICE_UPLOAD batch and check if record created in IM_DOC_HEAD,IM_DOC_DETAIL_REASON_CODES. 5. Check for REASON_CODE_ID in IM_DOC_DETAIL_REASON_CODES which will be NULL Ideally, the system should default the reason code as part of automatic debit Refer to the Debit Memo Details Note: As we are nearing the month-end and this issue needs to be addressed on priority As a Data fix to insert the reason code(12100) in the IM_DOC_DETAIL_REASON_CODES table to post the invoice. | 740964 | 2021-11-30 14:22 |  |  | 6:10 | SLA Violated | 2021-11-30 16:32 | FALSE |  | RMFCS Vendor Support | High | 1 |  | 37587 |  |  |  | SR 3-27857339571 | Carlos Costa | No status changes OWC with Oracle | SR Update: GPAPPANNAN@PANDA.COM.SA - Thursday [Update from Customer] Hi Rane, Please share the OWC details to join the meeting. Regards Guna GPAPPANNAN@PANDA.COM.SA - 6 days ago [Update from Customer] Dear Rene, Shall we do it on 30-Dec-21 @9:00 PM (KSA). Please confirm. Regards Guna INC UPDATE Gunasekaran Pappannan added a public note 6 days ago (Wed, 29 Dec, 2021 at 13:21) Hi Joao, Shall we do it on 30-Dec-21 @9:00 PM (KSA). Please confirm. Regards Guna Oracle Services Management Oracle Services Management replied 6 days ago (Wed, 29 Dec, 2021 at 19:12) Replied to : gpappannan@panda.com.sa Hi Guna, Yes for us its ok. Lets wait for the confirmation from Oracle. Best regards. | 20 | Urgent |  |  | Savola Tower |  |  |  |  | gpappannan@panda.com.sa | 9986739790 | Gunasekaran Pappannan |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  |  | After performing RCA, ReIM EDI Injector Batch Inserts Reason Code As Null For Debit Memo Cost Document- Failed in Invoice Posting |  |  |  |  | Incident | 0:00 |  | 2021-12-29 19:12 | High |  |  | All Locations
|  | Retail |  |  | 2021-12-01 20:20 |  |  | Information Technology | Error Message Failure processing integration Detailed Error Message Error Reason: java.lang.Exception: Invoke failed to generate a response within the timeout window. The endpoint invoked may be running slow or failing to execute altogether. Additional information for this endpoint execution will be captured in the Connectivity Agent logs. Please review, correct the failing condition and resubmit.:Application Error Error Summary: ICS runtime execution error | 741642 | 2021-12-02 00:20 |  |  | 0:15 | Within SLA | 2021-12-01 20:35 | FALSE |  | Integration Vendor Support Group | High | 1 |  | 37914 |  |  |  | 3-27942362171 | Luis Martins |  |  | 38 | Urgent |  |  | Savola Tower |  |  |  |  | logicsupport@panda.com.sa |  | Logic Support |  |  |  | RIB Vendor Support | Phone | Ready for Deployment â€“ Non Prod |  |  | SABS | OIC Exc id: 603857 Instance id: 22327287 ID904TransactionFileSABStoIDSFTPSched |  |  |  |  | Incident | 0:00 |  | 2021-12-28 16:55 | High |  |  | My Team
|  | Retail |  |  | 2021-12-02 09:08 |  |  | Supply Chain | Dear Team, Please kindly cancel the below process ID which is in progress status more than a week. | 741719 | 2021-12-08 13:08 |  |  | 0:17 | Within SLA | 2021-12-02 09:25 | FALSE |  | RMFCS Vendor Support | Low | 1 |  | 38835 |  |  |  | 3-28085817001 | Rui Machado | ANTONIO.A.COSTA@ORACLE.COM - Tuesday [Retail] Thank you Ivan, You just need to ask approval and share the DML with Panda, as we do in hotfixing scenario. Tell us if we can close this SR. Best Regards Antonio Costa Oracle Global Customer Support | JOAO.FONTAO@ORACLE.COM - 18+ hours ago [Retail] Hello Rui, Thanks! We are starting to close this SR. Best Regards, João Fontão Oracle Global Customer Support | 10 | Low | Can you please let me know if your facing any issue with sim application and share more details. If not kindly assign the ticket to the respective team. I will check and confirm. Create an SR to oracle to cancel this Transfer. We need to know why the Transfer status 'In Progress' ? |  | Savola Tower |  |  |  |  | jchavez@panda.com.sa | 537457930 | James Albert Chavez |  |  |  | RMFCS Vendor Support | Portal | Pending With Vendor |  |  | REIMCS | MUT Process ID Status |  |  |  |  | Incident | 0:00 |  | 2021-12-23 14:11 | Low |  |  | My Team
|  | Retail |  |  | 2021-12-02 10:15 |  |  | Operations | Dear IT team, Pleas check the below attached during the last fresh food we counter this issue SKU - 100211751 1- 22-Nov wrong enter QTY authorization by 1,002,122 Pc's entered 2- 22- Nov this wrong QTY flown to RMFCS by 143,123,540 PC's 3- Difference in QTY between SIM and RMFCS = -858,998 PC's 4- 30 - Nov Store correct this transaction with QTY -1,002,122 PC's 5- 30 Nov SIM SOH is corrected 5- 30 Nov this transaction flown to RMFC by the same QTY. The issue solved in SIM and store level but still as is in RMFCS due to different QTY flown to RMFCS = 858,998 PC's Need your support to solve the issue. | 741746 | 2021-12-08 14:15 |  |  | 2:37 | Within SLA | 2021-12-02 12:52 | FALSE |  | SIM Vendor Support Group | Low | 1 | [6 empty] | Carlos Pinho |  |  | 15 | Low | Hello, BUG 33106835 fixed on 16.0.3.7. to validate after upgrade. |  | Savola Tower |  |  |  |  | mamahmoud@panda.com.sa | 508393228 | Mahmoud Mostafa |  |  |  | Oracle Services Management | Portal | Pending |  |  | Oracle SIM Application | RMFCS data mismatch Cycle Count JDA#207 (124M difference ) |  |  |  |  | Incident | 0:00 |  | 2021-12-21 18:16 | Low |  |  | All Locations
|  | Retail | Reporting Issue |  | 2021-12-05 14:57 |  |  | Operations | Version:1.0 StartHTML:0000000105 EndHTML:0000038518 StartFragment:0000037931 EndFragment:0000038478 Kindly I need your support to submit attached dumbing under CEÃ¢â‚¬Â¦ I try to close but I cant 1285900 1292675 1310753 | 742743 | 2021-12-12 09:57 |  |  | 1:26 | Within SLA | 2021-12-05 16:23 | FALSE |  | SIM Vendor Support Group | Low | 2 |  | 39417 |  |  |  |  | Carlos Pinho |  |  | 2 | Low | No response from client |  | Stores |  |  |  |  | gm40008@panda.com.sa | 541268555 | GM 40008 |  |  |  | SIM Vendor Support | Portal | Open | East | 40008 | Oracle SIM Application | sim issue |  |  |  |  | Incident | 0:00 |  | 2022-01-02 12:01 | Low |  |  | Only me
|  | Supply Chain Oracle Inventory | Functional Issue |  | 2021-12-06 10:10 |  |  | Information Technology | Pack Item SOH Is not in line with the component item in RMFCS. Pack Item: 3187590 Component Item: 449520 Average weight: 7.25 Pack Item SOH Iniital ( Migrated from JDA)
|  | Supply Chain Oracle Inventory |  |  | 2021-12-06 13:38 |  |  | Information Technology | Hi, While analysing the issue for INC-742959 it came to notice that for one of the pix file PIX099352 (as attached) only 25600 records got loaded and remaining 3098 records were not loaded. If there was any error in loading ideally the records in STG_MANHT_PIX_IN should be rolled back but that didn't happen and in next run it started failing with integrity constraint issue. Please check and let know if there is a gap in code on exception for rollback? Regards, Amjad. | 743095 | 2021-12-09 10:38 |  |  | 37:22 | SLA Violated | 2021-12-12 15:00 | FALSE |  | Integration Vendor Support Group | Low | 1 |  | 38212 |  |  |  | 3-28032710631 | Luis Martins |  |  | 15 | Medium |  |  | Savola Tower |  |  |  |  | aalsaiyed@panda.com.sa |  | Amjad Saiyed |  |  |  | RIB Vendor Support | Phone | Pending With Vendor |  |  |  | ID901 MH PIX to IDS interface partial data load issue |  |  |  |  | Incident | 0:00 |  | 2021-12-29 10:42 | Medium |  |  | All Locations
|  | Integration Layer |  |  | 2021-12-10 05:00 |  |  |  | Hello Gatha, ZIP_FILE_WAIT_JOB is long running. It is waiting for the ZIP files to proceed further. Could you please check and do the needful for the batch progress. Thanks & Regards, Venkatesh Nishtala Batch Monitoring L1 Support Team [cid:image002.gif@01D6F896.7A913D90] Logic Information Systems (INDIA) Pvt Ltd. Kochar Technology Park, 4th Floor, #SP-31A Ambattur Industrial Estate, Ambattur, Chennai, 600 058 INDIA. [cid:image003.png@01D6F896.7A913D90]<http://www.logicinfo.com/> [cid:image004.png@01D6F896.7A913D90] <http://www.facebook.com/logicretail> [cid:image005.png@01D6F896.7A913D90] <http://www.twitter.com/logicretail> [cid:image006.png@01D6F896.7A913D90] <http://www.linkedin.com/company/logic-information-systems> The contents of this email message and any attachments are intended solely for the addressee(s) and may contain Logic confidential and/or restricted information and may be legally protected from disclosure. If you are not the intended recipient of this message, or if this message has been addressed to you in error, please immediately alert the sender by reply email and then delete this message and any attachments. If you are not the intended recipient, you are hereby notified that any use, dissemination, copying, or storage of this message or its attachments is strictly prohibited. | 744473 | 2022-01-02 11:42 |  |  | 11:45 | Within SLA | 2021-12-10 16:45 | FALSE |  | Integration Vendor Support Group | Low | 7 |  | 38156 |  |  |  | 3-28087581361 | Carlos da Costa |  |  | 15 | Low | Can you confirm if the password of the user ORCA_INT changed recently? New update made on the SR, with some concerns related to the ODI workaround process code. Can you check the points mentioned by Oracle in order to raise a new SR? |  | Savola Tower |  |  |  |  | nishtala.venkatesh@logicinfo.com |  | Nishtala Venkatesh |  |  |  | RIB Vendor Support | Email | Pending With Vendor |  |  | POM | ZIP_FILE_WAIT_JOB is Long Running |  |  |  |  | Incident | 0:00 |  | 2021-12-29 19:12 | Low |  |  | My Team
|  | Retail | Identity and Access |  | 2021-12-13 13:49 |  |  | Supply Chain | We have the negative SOH in RMFCS seems which is not matching with the WMS SOH. Pls check whether any integration issues still not cleared. Pls refer the attached file | 745541 | 2021-12-14 12:49 |  |  | 0:01 | Within SLA | 2021-12-13 13:50 | FALSE |  | RMFCS Vendor Support | High | 6 |  | 38377 |  |  |  |  | Carlos Costa |  |  | 9 | High | I will look at this issue. There are some delay in the system. Kindly, check now it should be no mismatch. |  | Distribution Centre |  |  |  |  | rwarrier@panda.com.sa | 532739767 | Rajeev Warrier |  |  |  | RMFCS Vendor Support | Portal | Open | DC993 |  | REIMCS | Negative SOH |  |  |  |  | Incident | 0:00 |  | 2022-01-02 09:29 | High |  |  | All Locations
|  | Retail |  |  | 2021-12-16 15:04 |  |  | Information Technology | Hi, The flow for IBMPOS ended with 'PE' for process_id 1464 (this can be viewed at table IDS_PRICE_EXPORT_CTRL). This issue originates from the fact that OIC was taking time to start processing the request made by the KSH (remember OIC has a pooling mechanism - which may grow momentarly when there are many simulaneous requests). We never saw that problem occur with that integration before - likelly there were many requests to OIC at that moment of the execution. What it did is that every thread completed successfully (so all data sent to IIB), but the POST_PROCESSOR function, which looks at the state of all threads to decide the final status, was launched before all threads were finished, so that's why it considered there were issues and put status 'PE'. That same kind of issue existed before, but was because the processing was taking too long to finish
|  | Retail | Functional Issue |  | 2021-12-16 17:14 |  |  | Commercial | Dear IT Team, Please check what is the issue as we process MASS UPLOAD TRANSFER yesterday with Process ID 7650. then when I export all transfer in excel file, Panda 207 have a double transfer for Banana which will cause of overstock to their store. please check the issue to avoid this will happen again. TransferFrom LocationFrom Location NameTo LocationTo Location NameCreated DateDelivery DateStatus 1996551726000.WH "No# 991 RABIGH-Virtual58.SM No 207 MADAEN AL FAHAD AREA JEDDAH12/15/2112/15/21Approved 1996844026000.WH "No# 991 RABIGH-Virtual58.SM No 207 MADAEN AL FAHAD AREA JEDDAH12/15/2112/15/21Approved Thanks | 747199 | 2021-12-23 12:00 |  |  | 65:11 | SLA Violated | 2021-12-19 10:26 | FALSE |  | RMFCS Vendor Support | Low | 7 |  | 38700 |  |  |  | 3-28074613881 | Carlos Pinho | JOAO.FONTAO@ORACLE.COM - 10 days ago [Retail] Hello Rui This error occurred because of thread control and because there are two weblogics bean consuming the same table in parallel. But with the CR81 this thread control will be more robust, which will make this scenario stop happening. This problem is a very rare scenario, and we've only seen this case. Please, tell us if you prefer to close this SR or leave it opened at Panda side until the installation of the CR. Best Regards João Fontão Oracle Global Customer Support | No status changesHi, Collecting information regarding CR81 planning in order to update this ticket. Best regards, José Aguiar | 10 | Low | Fix will be available with deployment of CR81. CR81 is planned for January 2022. This ETA has been provided by ORC team. Requested further clarification to Oracle in the SR. |  | Regional Office |  |  |  |  | esinson@panda.com.sa | 569839567 | Ernie Sinson |  |  |  | No Agent | Portal | Pending With Vendor | West |  | Oracle SIM Integration | Double transfer in one process ID |  |  |  | CR81 | Incident | 0:00 |  | 2021-12-28 18:18 | Low |  |  | My Team
|  | Retail |  |  | 2021-12-17 13:08 |  |  | Information Technology | SR 3-26337055821 : UDA Length not checked in UI I was noticed that the UDA Length is not being checked when updating Free Form UDA's using the UI. An UDA has length set to 7 but the Item UDAs screen allows to set text longer than 7 chars for the UDA. This validation existed in previous RMS versions and this has impact in interfacing data to external systems which work on fixed length formats. For certain interfaces and target systems, a Fixed Data Length attribute flat file is needed to be produced. When using Free Form UDAs, we have no way to ensure that the information being exported fits on the destination flat file format. Given RMS had length validation functionality before, request is to re-introduce a validation on the UDA data in order to support such scenarios and avoid introducing unsupported data into the overall customer's systems. | 747359 | 2021-12-23 12:00 |  |  | 0:00 | Within SLA | 2021-12-17 13:09 | FALSE |  | RMFCS Vendor Support | Low | 1 |  | 38510 |  |  |  | 3-26337055821 | Carlos Costa | No status changes | No status changes | 5 | Low |  |  | Savola Tower |  |  |  |  | rmfcsptassets@panda.com.sa |  | RMFCS Project Team |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  | RMS | PGL - SR 3-26337055821 : UDA Length not checked in UI |  |  |  |  | Incident | 0:00 |  | 2021-12-28 18:22 | Low |  |  | My Team
|  | Financials Oracle Payables | Reporting Issue |  | 2021-12-19 13:31 |  |  | Information Technology | Dear RC Team, Request to mass update of the following CFA's in the production environment. 1. Supplier Name in Arabic(SUPS_CFA_EXT) 2. Address Line 1 in Arabic(ADDR_CFA_EXT ) 3. Address Line 2 in Arabic(ADDR_CFA_EXT ) The data needs to be updated in the below two tables SUPS_CFA_EXT and ADDR_CFA_EXT You will receive the data from the business in a day or two, could you please raise an Oracle Support Request for this. The Oracle team can prepare the script and keep it ready for you. | 747959 | 2021-12-29 16:55 |  |  | 0:26 | Within SLA | 2021-12-19 13:57 | FALSE |  | RMFCS Vendor Support | High | 1 |  | 38580 |  |  |  | 3-28043778341 | Carlos Costa | No status changes | No status changes | 13 | Urgent | Oracle has a few questions regarding the shared file. Can you please review? Oracle need the script/information to updated from backend. |  | Savola Tower |  |  |  |  | gpappannan@panda.com.sa | 507862074 | Gunasekaran Pappannan |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  |  | Request mass upload off CFA's for Arabic data - Supplier & Address |  |  |  |  | Incident | 0:00 |  | 2022-01-01 15:24 | High |  |  | All Locations
|  | Retail | Functional Issue |  | 2021-12-21 16:55 |  |  | Information Technology | Dear Oracle Team, Next week business team are going to do reclassification with the same department (moving item from one class/subclass to another within same department number) for many items. We need to know whether it will trigger any changes and send to downstream systems (POS/SIM/CB/infoera ...etc) or not. System is sending the changes in case of department change. In this situation, there is no department change will happen. Kindly analyse and share your feedback at earliest. Regards, Ayen Uddin. | 748866 | 2021-12-22 15:55 |  |  | 0:05 | SLA Violated | 2021-12-21 17:30 | FALSE |  | RMFCS Vendor Support | High | 1 |  | 38752 |  |  |  |  | Carlos Costa |  |  | 6 | High |  |  | Savola Tower |  |  |  |  | auddin@panda.com.sa |  | Ayen Uddin |  |  |  | RMFCS Vendor Support | Phone | Open |  |  | RMS | Impact in downstream systems (POS, CB, SIM etc.) while reclassification happen within the department |  |  |  |  | Incident | 0:00 |  | 2021-12-26 13:32 | High |  |  | All Locations
|  | Retail |  |  | 2021-12-23 16:04 |  |  | Super Stores | dear team, we need your support to check the attached item we cannot print shelf tag because it is not coming thank you | 749784 | 2021-12-30 11:49 |  |  | 0:02 | Within SLA | 2021-12-23 16:06 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | Low | 2 |  | 38930 |  |  |  |  | Second hoice |  |  | 2 | Low | Please create new price changes for these items. |  | Stores |  |  |  |  | smp428@panda.com.sa | 542011578 | Store Manager P428 |  |  |  | No Agent | Portal | Pending | East | 428 | Oracle SIM Integration | item not showing shelf tag |  |  |  |  | Incident | 0:00 |  | 2021-12-29 19:58 | Low |  |  | Only me
|  | Retail |  |  | 2021-12-23 18:49 |  |  | Information Technology | Please check we have some records with H status in STG_MANHT_PICKTICKET_HEAD_IN table | 749819 | 2021-12-28 14:00 |  |  | 0:00 | Within SLA | 2021-12-24 02:18 | FALSE |  | Integration Vendor Support Group | Medium | 1 |  | 38874 |  |  |  |  | Carlos Costa |  |  | 4 | Medium |  |  | Distribution Centre |  |  |  |  | jwehbe@panda.com.sa | 5446551654 | Jamal Ali Wehbe |  |  |  | RIB Vendor Support | Phone | Open | DC993 |  | RMS | Records with Error in STG_MANHT_PICKTICKET_HEAD_IN Table |  |  |  |  | Incident | 0:00 |  | 2022-01-02 13:31 | Medium |  |  | All Locations
|  | Retail |  |  | 2021-12-23 18:55 |  |  | Information Technology | Dear Luis, please check STG_MANHT_PIX_IN table holding more than 38K records in H status Regards | 749821 | 2021-12-28 14:00 |  |  | 0:00 | Within SLA | 2021-12-23 22:09 | FALSE |  | Integration Vendor Support Group | Medium | 1 |  | 38870 |  |  |  |  | Luis Martins |  |  | 12 | Medium |  |  | Distribution Centre |  |  |  |  | jwehbe@panda.com.sa | 5446551654 | Jamal Ali Wehbe |  |  |  | RIB Vendor Support | Phone | Open | DC993 |  | RMS | Records with Error in STG_MANHT_PIX_IN Table |  |  |  |  | Incident | 0:00 |  | 2021-12-31 01:34 | Medium |  |  | All Locations
|  | BI Retail & Store Operations |  |  | 2021-12-25 11:29 |  |  |  | Dear Team, Please need your support kindly maximize report captures Data, we are unable to captures reports. thanks Stock_Transfer_Report - Oracle Analytics Publisher (oracleindustry.com) | 750035 | 2021-12-30 12:00 |  |  | 4:19 | SLA Violated | 2021-12-26 12:19 | FALSE |  | RMFCS Vendor Support | Low | 1 |  | 38931 |  |  |  |  | Carlos Costa |  |  | 1 | Low |  |  | Distribution Centre |  |  |  |  | dchelpdeskkaec@panda.com.sa | 538274471 | DC Helpdesk-KAEC |  |  |  | RMFCS Vendor Support | Portal | Open | DC991 (KAEC) |  |  | RMFCS Report [Stock Transfer Report] |  |  |  |  | Incident | 0:00 |  | 2022-01-02 11:08 | Low |  |  | All Locations
|  | Retail | Reporting Issue |  | 2021-12-25 16:05 |  |  | Operations | Dear, Kindly need your support to update correct prices in pos . shelf tag and pos price different . please find the attached file. Sku Description Shelf tag price POS price 100224138 klasse apple beer 2.05 8 | 750102 | 2022-01-02 14:23 |  |  | 16:41 | SLA Violated | 2021-12-27 15:41 | FALSE |  | RMFCS Retail Finance and Pricing vendor support | Low | 1 |  | 38970 |  |  |  |  | Second hoice |  |  | 2 | Low | Waiting for reporter to apply suggestion and confirm issue resolved or provide further comment in case it's not resolved. |  | Stores |  |  |  |  | wsanchez@panda.com.sa | 582655183 | Wennie WSanchez |  |  |  | No Agent | Portal | Pending | West | 20009 | Oracle SIM Integration | Price discrepancy - regular shelf tag price and pos price different |  |  |  |  | Incident | 0:00 |  | 2021-12-28 21:24 | Low |  |  | My Team
|  | Supply Chain Oracle Procurement |  |  | 2021-12-26 10:31 |  |  | Information Technology | ILR upload is not checking if the item-location has an active PO/TO before updating their status to Inactive. This causes messages in RIB to get stuck and need manual intervention to fix | 750276 | 2021-12-28 16:31 |  |  | 0:04 | Within SLA | 2021-12-26 10:35 | FALSE |  | RMFCS Vendor Support | Medium | 1 |  | 38932 |  |  |  | 3-28136613361 (Assets), 3-28155641321 (Cloud) | Carlos Costa | No status changes | No status changes | 5 | Medium |  |  | Savola Tower |  |  |  |  | gpappannan@panda.com.sa | 507862074 | Gunasekaran Pappannan |  |  |  | RMFCS Vendor Support | Phone | Pending With Vendor |  |  |  | When the Item Location status changes from Active to Inactive, the ILR upload does not check the Open PO/TO status |  |  |  |  | Incident | 0:00 |  | 2022-01-02 17:09 | Medium |  |  | All Locations
|  | Retail | Functional Issue |  | 2021-12-26 12:17 |  |  | Information Technology | Hi, I would like to confirm if the table 'ORCA_PO_ACKNOWLEDGE_STATUS' and 'ORCA_PO_DOWNLOAD_STATUS' field 'CREATE_DATETIME' is logged based on when user download or acknowledge the PO. I had seen some inconsistency where it was not capturing 'create_datetime' based on when user / supplier acknowledge or download the PO. Business wanted to measure if this is the right field to calculate when the PO is created in ORDHEAD and create datetime is logged versus when it's been downloaded or acknowledged on supplier portal. Note, in the technical document it's not very clearly mentioned and it would be absolutely wrong to make any assumption. Regards, Junaid Alam | 750345 | 2021-12-29 09:17 |  |  | 0:27 | Within SLA | 2021-12-26 12:44 | FALSE |  | RMFCS Vendor Support | Medium | 1 |  | 38933 |  |  |  | 3-28129645471 | Carlos Costa | No status changes | No status changes | 6 | Medium | SR 3-28129645471 created in order for Oracle to help clarify the question. |  | Savola Tower |  |  |  |  | jalam@panda.com.sa |  | Junaid Alam |  |  |  | RMFCS Vendor Support | Portal | Pending With Vendor |  |  | RMS | Supplier Portal download / acknowledgement logging confirmation |  |  |  |  | Incident | 0:00 |  | 2022-01-02 09:48 | Medium |  |  | My Team
|  | Supply Chain Oracle Inventory |  |  | 2021-12-27 12:49 |  |  | Information Technology | Dear RC Team, Our business team received a PO in Manhattan and noticed that the receiving quantity is double in RMFCS. We have noticed that the receipt qty in staging table( stg_manht_receipt_in) is correct. In the following LPNs, the receipt quantity is double in RMFCS Please investigate the issue on priority. PO NO:52935512 Item: 100205097 Please check below LPNs where its showing 150 units in your file while WMS we sent only 75 for each LPN and that is the exact variance, also I can see in STD_MANHT_RECEIPT_IN that also holding 75units select * from stg_manht_receipt_in where item='100205097' and po_nbr='52935512' and case_nbr in ( 'FF0024977265', 'FF0024977266', 'FF0024977267', 'FF0024977268', 'FF0024977269', 'FF0024977270', 'FF0024977271', 'FF0024977272', 'FF0024977273', 'FF0024977274', 'FF0024977275', 'FF0024977276', 'FF0024977277', 'FF0024977278', 'FF0024977279', 'FF0024977280', 'FF0024977281', 'FF0024977282', 'FF0024977283', 'FF0024977284', 'FF0024977285', 'FF0024977286')
|  | Retail |  |  | 2021-12-29 18:18 |  |  | Supply Chain | Dear Team, please advise of the attached POs that we have discover still in approved sts while it is passed the not after date, this orders are affecting all replenishment systems in the company what may ends with empty shelf in the stores, please investigate and solve the issue. | 751654 | 2022-01-03 14:00 |  |  | 1:52 | Within SLA | 2021-12-30 09:52 | FALSE |  | Integration Vendor Support Group | Low | 2 |  | 39437 |  |  |  |  | Vitor Goncalves |  |  | 4 | Medium | wait for details |  | Savola Tower |  |  |  |  | ambahmaid@panda.com.sa | 568755222 | Abdulrahman Bahmaid |  |  |  | RIB Vendor Support | Portal | Open |  |  | RMS | Orders still in approved sts while it is passed the not after date |  |  |  |  | Incident | 0:00 |  | 2022-01-02 16:13 | High |  |  | All Locations
|  | Retail | Reporting Issue |  | 2021-12-30 08:08 |  |  | Operations | Dear Team, kindly see the below container number not found in system but we already receive items. please do your needful as you know tomorrow is closing year. JC0003725818 JC0003725819 JC0003725820 | 751710 | 2022-01-03 09:51 |  |  | 3:36 | Within SLA | 2021-12-30 11:44 | FALSE |  | Integration Vendor Support Group | Low | 2 |  | 39151 |  |  |  |  | Second hoice |  |  | 4 | Low |  |  | Stores |  |  |  |  | rcvr227@panda.com.sa | 5657655826 | Rcvr panda 227 |  |  |  | RIB Vendor Support | Portal | Open | West | 227 | Oracle SIM Integration | Container Number |  |  |  |  | Incident | 0:00 |  | 2021-12-31 15:59 | Low |  |  | All Locations
|  | Retail | Reporting Issue |  | 2021-12-30 11:24 |  |  | Supply Chain | Dear SIM Team, - Write-off was done for closed location Panda 234 and FC 775 on 29th Dec 2021 but adjustment didn't flow to RMFCS, Please check and update. - Please find below details related to this subject: JDA SIM RMS Count ID SIM Count ID 775 775 10000904 141861 234 487 10000888 141893 Kind Regards , | 751809 | 2021-12-30 15:24 |  |  | 0:25 | Within SLA | 2021-12-30 11:49 | FALSE |  | RMFCS Vendor Support | Low | 2 |  | 39322 |  |  |  | 3-28143746441 | Bruno Melo | No status changes | No status changes | 10 | Urgent | Cloud team has executed the script and it will reprocess by nightly batch. |  | Savola Tower |  |  |  |  | rmohammed@panda.com.sa | 501788703 | Rafiudeen Mohammed |  |  |  | RMFCS Vendor Support | Portal | Pending With Vendor |  |  | Oracle SIM Integration | Closed Location (Write-off) P234 & FC775 |  |  |  |  | Incident | 0:00 |  | 2022-01-02 10:10 | Low |  |  | My Team
|  | IT Operation Maintenance |  |  | 2021-12-30 14:06 |  |  | Information Technology | Integration test between Mantis and MyService. This incident will not be accounted. | 751938 | 2022-01-06 11:37 |  |  | 0:13 | Within SLA | 2021-12-30 14:19 | FALSE |  | Integration Vendor Support Group | Low | 1 | [6 empty] | Carlos Pinho |  |  | 1 | Low | test |  | Savola Tower |  |  |  |  | oraclesm@panda.com.sa |  | Oracle Services Management |  |  |  | RIB Vendor Support | Email | Open |  |  | Handheld | Integration Test between Mantis and MyService |  |  |  |  | Incident | 0:00 |  | 2021-12-31 14:35 | Low |  |  | Only me
|  | Retail | Functional Issue |  | 2021-12-30 15:42 |  |  | Merchandising | Valid PO is received in handheld, when check in SIM showing Qty as Zero. | 752013 | 2022-01-06 10:42 |  |  | 66:30 | SLA Violated | 2022-01-02 10:12 | FALSE |  | RMFCS Vendor Support | Low | 5 |  | 39418 |  |  |  |  | Vitor Goncalves |  |  | 3 | Low |  |  | Stores |  |  |  |  | rcvr40004@panda.com.sa | 561954403 | Rcvr 40004 |  |  |  | RMFCS Vendor Support | Portal | Open | East | 40004 | Oracle SIM Integration | SIM showing ZERO Qty |  |  |  |  | Incident | 0:00 |  | 2022-01-03 11:06 | Low |  |  | My Team
|  | Retail | Reporting Issue |  | 2021-12-31 11:35 |  |  | Operations | Dear team, Need your support to update the attached container IDs, Its already received physically. | 752253 | 2022-01-06 12:00 |  |  | 4:04 | SLA Violated | 2022-01-02 12:04 | FALSE |  | SIM Vendor Support Group | Low | 1 |  | 39415 |  |  |  |  | Second hoice |  |  | 1 | Low |  |  | Stores |  |  |  |  | rcvr170@panda.com.sa | 571974517 | Rcvr 170 |  |  |  | Oracle Services Management | Portal | Open | Central1 | 170 | Oracle SIM Integration | Container id not updated |  |  |  |  | Incident | 0:00 |  | 2022-01-02 12:04 | Low |  |  | My Team
|  | Retail | Functional Issue |  | 2021-12-31 16:29 |  |  | Operations | Dear Team need your support to check ZAMZAM sales in system we notice that some time system not updating sales. 100217963 â”‚ ZAMZAM WATER 5L â”‚ PCS â”‚ 5L â”‚ 5.50 | 752304 | 2022-01-06 11:53 |  |  | 4:04 | SLA Violated | 2022-01-02 12:04 | FALSE |  | SIM Vendor Support Group | Low | 1 | [6 empty] | Vitor Goncalves |  |  | 1 | Low |  |  | Stores |  |  |  |  | rcvr237@panda.com.sa | 582247330 | Rcvr 237 |  |  |  | Oracle Services Management | Portal | Open | West | 237 | Oracle SIM Integration | Zamzam Sales Not Updated In System |  |  |  |  | Incident | 0:00 |  | 2022-01-02 12:04 | Low |  |  | My Team
|  | Retail | Functional Issue |  | 2021-12-31 20:16 |  |  | Operations | Team we would like to inform you that the barcode on the attached wasn't found on the system during scanning the item on the POS. Kindly we need your support to activate the barcode. Thanks | 752330 | 2022-01-04 13:52 |  |  | 0:00 |  |  | FALSE |  | Integration Vendor Support Group | High | 1 | [6 empty] | Second hoice |  |  | 0 | Medium |  |  | Stores |  |  |  |  | mcampiao@panda.com.sa | 551160760 | Moamar Campiao |  |  |  | RIB Vendor Support | Portal | Open | Central1 | 10010 | Oracle SIM Integration | Item not found |  |  |  |  | Incident | 0:00 |  | 2021-12-31 20:24 | Low |  |  | My Team
|  | Retail |  |  | 2022-01-01 16:04 |  |  | Information Technology | Hi Team, The killer promotions did not reach the POS for Jan 1st 2022 we have attached the details of the items and the process id is 1628. As this process are not integrated to Point of sales we have cancelled the offer and re-created promotion and those promotions are flown to POS. Can you investigate why the particular offer (1628) is not integrated. Regards, Preethi | 752527 | 2022-01-02 16:01 |  |  | 6:58 | SLA Violated | 2022-01-02 14:58 | FALSE |  | Integration Vendor Support Group | Medium | 1 |  | 39438 |  |  |  | SR 3-28148925631 | Carlos Costa |  |  | 1 | High |  |  | Savola Tower |  |  |  |  | logicsupport@panda.com.sa |  | Logic Support |  |  |  | RIB Vendor Support | Portal | Open |  |  | RMS | Killer Promotions did not reach POS for Jan 1st 2022 |  |  |  |  | Incident | 0:00 |  | 2022-01-02 14:59 | High |  |  | My Team
|  | Retail | Functional Issue |  | 2022-01-02 14:06 |  |  | Operations | Dear team As we check our POS transaction yesterday, we notice that sim start capturing the POS transaction around 10:43 pm. please find the attached file for reference. please need your support for this issue | 752854 | 2022-01-09 09:06 |  |  | 2:54 | Within SLA | 2022-01-02 17:16 | FALSE |  | SIM Vendor Support Group | Low | 1 | [6 empty] | Second hoice |  |  | 1 | Low |  |  | Stores |  |  |  |  | vmatorre@panda.com.sa | 571446911 | Vergel Gludo Matorre |  |  |  | Oracle Services Management | Portal | Open | West | 20001 | Oracle SIM Integration | sim issue (pos transaction missing) |  |  |  |  | Incident | 0:00 |  | 2022-01-02 17:16 | Low |  |  | My Team
|  | Retail | Functional Issue |  | 2022-01-02 15:10 |  |  | Operations | Dear team Please find the attached file for the items that we sold yesterday (cellphone) but as we check the sim for the pos transaction the available pos transaction (receipt) is not showing in the sim pos transaction. And also the system and physical quantity is not matching. please find the attached file for reference. Please need your support and advice for this issue. Thanks and regards | 752901 | 2022-01-09 10:10 |  |  | 1:50 | Within SLA | 2022-01-02 18:19 | FALSE |  | SIM Vendor Support Group | Low | 1 |  | 39459 |  |  |  |  | Carlos Costa |  |  | 1 | Low |  |  | Stores |  |  |  |  | vmatorre@panda.com.sa | 571446911 | Vergel Gludo Matorre |  |  |  | Oracle Services Management | Portal | Open | West | 20001 | Oracle SIM Integration | cellphone issue (system not update) |  |  |  |  | Incident | 0:00 |  | 2022-01-02 18:20 | Low |  |  | My Team
|  | Supply Chain Oracle Procurement | Functional Issue |  | 2022-01-03 09:45 |  |  | Information Technology | Business user created import purchase order via induction process populate wrong currency exchange rate. The same has been re-created in stage(test) environment. When user prepare the spread sheet without exchange rate/currency, system by default picking the exchange rate as "1" instead of "3.75". When the user creates via UI by default it is populating 3.75. Example: PO No: 50948855 Currency : USD Exchange Rate: 3.75 | 753078 | 2022-01-03 13:45 |  |  | 0:00 |  |  | FALSE |  | RMFCS Vendor Support | High | 1 | [6 empty] | Carlos Costa |  |  | 0 | Urgent |  |  | Savola Tower |  |  |  |  | gpappannan@panda.com.sa | 507862074 | Gunasekaran Pappannan |  |  |  | RMFCS Vendor Support | Phone | Open |  |  |  | Import Purchase Order created via Induction process is defaulting wrong exchange rate |  |  |  |  | Incident | 0:00 |  | 2022-01-03 09:45 | High |  |  | All Locations