## 20220216
Category | Classification | Created Time | Ticket Id | Due by Time | Group | Impact | Item | Mantis ID Ref. | Agent Name | Oracle SR | UPDATE AT 20220215 | UPDATE AT 20220216 | ORC L2 Agents | Priority | Requester Email | Requester Name | Agent | Status | Sub-Category | Subject | Last Updated Time | Urgency
Retail |  | 2021-09-14 17:57:02 | 712433 | 2021-09-21 12:00:00 | RMFCS Vendor Support | Medium |  | 34586 |  | SR 3-27167309171 | No status changes since last RC update. | No status changes since last RC update. | Vitor Goncalves | Low | rmfcsptassets@panda.com.sa | RMFCS Project Team | RMFCS Vendor Support | Pending With Vendor | RMS | RMFCS - CW items - Case Weight definition is not mandatory | 2022-02-11 12:31:59 | Medium
Financials Oracle Receivables |  | 2021-09-30 11:14:31 | 719205 | 2021-09-30 15:14:31 | RMFCS Retail Finance and Pricing vendor support | High |  | 34840 |  | Severity 1 SR 3-27241839551 | No status changes since last RC update. | No status changes since last RC update. | Bruno Melo | Urgent | rlasmal@panda.com.sa | Ram Lamsal | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor |  | Unable to resolve invoices due to qty Decimal issue | 2022-02-11 12:35:27 | High
Retail |  | 2021-09-12 09:28:37 | 710925 | 2021-09-14 15:28:37 | Integration Vendor Support Group | High |  | 34150 |  | 3-28401867611 |  |  | Luis Martins | Medium | jwehbe@panda.com.sa | Jamal Ali Wehbe | RIB Vendor Support | Pending With Vendor | RMS | Manhattan-Missing files under MFCS_INBOUND_FILES | 2022-02-14 19:23:05 | Medium
Retail |  | 2021-10-14 15:05:54 | 724576 | 2021-10-14 19:05:54 | RMFCS Retail Finance and Pricing vendor support | Medium |  | 35567 |  | SR 3-27449790531 / Severity 1 SR 3-27665894791 | Last SRs updates: SR 3-27449790531: " Hello Wade Adam, Business has escalated the issue that the supplier payment has been pending for quite some time. Discuss the issue with the development team and provide a fix. Regards Guna" SR 3-27665894791: "Hi Bruno, We were not aware that recreating the same invoice is still having issue with discrepancy resolution. From the file SR_3-27665894791_Cannot_match_invoices_due_to_the_Application_Error_v2.xlsx provided by you, I understand that you are getting 'An application error occurred' error while trying to resolve the discrepancy using either Summary Match screen or Discrepancy Review List screen. Please let us know if you are facing the same issue after recreating the same invoice. Also, please let me know the exact date/time (including time zone) at which you had attempted to resolve the discrepancy. This is required to capture log file for any additional info. Thanks & Regards, Purna Singh" | Last SRs updates: Update from Oracle SR 3-27449790531: Oracle Support - 22+ hours ago [ODM Action Plan] Hello Bruno, Please confirm now that after scripts have been completed issue has been resolved Please note that your Service Request Number 3-27449790531 has been updated. To view the update, please access My Oracle Support at https://support.oracle.com/ and choose the Service Requests tab. ---- From the file SR_3-27665894791_Cannot_match_invoices_due_to_the_Application_Error_v2.xlsx provided by you, I understand that you are getting 'An application error occurred' error while trying to resolve the discrepancy using either Summary Match screen or Discrepancy Review List screen. Please let us know if you are facing the same issue after recreating the same invoice. Also, please let me know the exact date/time (including time zone) at which you had attempted to resolve the discrepancy. This is required to capture log file for any additional info. Thanks & Regards, Purna Singh" | Bruno Melo | Urgent | rlasmal@panda.com.sa | Ram Lamsal | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | REIMCS | In Summary Matching screen, the receipt Qty is showing negative value | 2022-02-14 10:30:01 | Medium
Retail |  | 2021-10-17 12:48:01 | 725494 | 2021-10-21 16:48:01 | RMFCS Vendor Support | Low |  | 35667 |  | 3-27606141781 | Last update from Oracle on the SR after RC update - 3-27606141781: Oracle Support - 13+ hours ago [Notes] Hi João, This issue is not reproducing internally and I have forwarded this to our internal team in order to gather insight from the Developers and Tech Team. When I have received some helpful feedback, I will let you know. We appreciate your patience. regards, Rene | No status changes since last update WIP with ORC. | Bruno Melo | Low | rlasmal@panda.com.sa | Ram Lamsal | RMFCS Vendor Support | Pending With Vendor | REIMCS | Unable to fetch data on discrepancy review list screen. | 2022-02-14 13:47:03 | Low
Financials Oracle Receivables | Functional Issue | 2021-11-01 14:22:17 | 731214 | 2021-11-08 09:22:17 | RMFCS Vendor Support | High |  | 36490 |  | SR 3-27596400571 | No status changes since last RC update. | No status changes since last RC update. | Bruno Melo | Low | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | User Unable to Match the Invoice with Receipt - Shows Tax Discrepancy | 2022-02-11 12:58:57 | High
Supply Chain Oracle Procurement |  | 2021-11-15 10:50:01 | 735830 | 2021-11-17 16:50:01 | RMFCS Vendor Support | Low |  | 36871 |  | SR 3-27696704841 | No status changes since last RC update. | No status changes since last RC update. | Carlos Costa | Medium | mraza@panda.com.sa | Mohd Raza | RMFCS Vendor Support | Pending With Vendor |  | Item Short Description Change in Item is not cascaded to Item Location Level | 2022-02-11 13:00:27 | Low
Retail |  | 2021-10-27 10:07:08 | 729445 | 2021-10-31 16:07:08 | RMFCS Vendor Support | Low |  | 36991 |  | SR 3-27562763471 | No status changes since last RC update. | No status changes since last update WIP with ORC. | Bruno Melo | Medium | wabdulaziz@panda.com.sa | Wail Abdulaziz | RMFCS Vendor Support | Pending With Vendor | REIMCS | Invoice is in un-resolved status & default from receipt is locked | 2022-02-14 13:52:28 | Low
Retail | Environment Issue | 2021-11-22 10:57:33 | 738440 | 2022-01-25 11:29:27 | RMFCS Retail Finance and Pricing vendor support | Medium |  | 37134 |  | No SR Created | Oracle Services Management added a public note a month ago (Wed, 1 Dec, 2021 at 13:55) Notified to : rpcsvsg@panda.com.sa This request has been shared with Mike and Kimberley in order to check how to provide the information and also develop an operational process that Panda can follow every time that is necessary. Waiting update from them in order to update the ticket. | Oracle Services Management added a public note a month ago (Wed, 1 Dec, 2021 at 13:55) Notified to : rpcsvsg@panda.com.sa This request has been shared with Mike and Kimberley in order to check how to provide the information and also develop an operational process that Panda can follow every time that is necessary. Waiting update from them in order to update the ticket. | Second hoice - Service manager | High | jalam@panda.com.sa | Junaid Alam | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | RMS | Cloud Patch deployment log | 2022-01-24 12:37:27 | High
Financials Oracle Receivables |  | 2021-11-28 17:45:33 | 740551 | 2021-11-28 21:45:33 | RMFCS Vendor Support | High |  | 37506 |  | SR 3-27832605471 | No status changes since last RC update. | No status changes since last RC update. | Carlos Costa | Urgent | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | Receiver Cost Adjustment (RCA) done in RMFCS Does Not Recalculate WAC | 2022-02-11 13:05:23 | High
Supply Chain Oracle Procurement | Functional Issue | 2021-11-16 16:28:22 | 736491 | 2021-11-17 15:28:22 | Integration Vendor Support Group | High |  | 36936 |  | 3-27735493111 | No status changes since last RC update. |  | Ray Milliati | High | gpappannan@panda.com.sa | Gunasekaran Pappannan | RIB Vendor Support | Pending With Vendor |  | PO Receipt Information is not interfaced from Manhattan to RMFCS | 2022-02-15 14:45:02 | High
Financials Oracle Payables | Functional Issue | 2021-11-30 10:22:29 | 740964 | 2021-11-30 14:22:29 | RMFCS Retail Finance and Pricing vendor support | High |  | 37587 |  | SR 3-27857339571 | No status changes since last RC update. | No status changes since last RC update. | Bruno Melo | Urgent | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor |  | After performing RCA, ReIM EDI Injector Batch Inserts Reason Code As Null For Debit Memo Cost Document- Failed in Invoice Posting | 2022-02-11 13:07:40 | High
Retail | Functional Issue | 2021-11-25 14:14:22 | 739680 | 2021-12-02 09:14:22 | RMFCS Vendor Support | Medium |  | 37609 |  | 3-24301935601 | No status changes since last RC update. | No status changes since last RC update. | Carlos Costa | Low | rmfcsptassets@panda.com.sa | RMFCS Project Team | RMFCS Vendor Support | Pending With Vendor | RMS | Catch Weight Sale Types are not validating Standard UOM in Item Creation | 2022-02-11 13:09:19 | Low
Retail |  | 2021-11-29 08:37:05 | 740623 | 2021-12-05 12:37:05 | SIM Vendor Support Group | Low |  | 37640 |  | SR 3-27874541491 | No status changes since last update WIP with ORC. | No status changes since last update WIP with ORC. | Carlos Pinho | Low | mamahmoud@panda.com.sa | Mahmoud Mostafa | SIM Vendor Support | Pending With Vendor | Oracle SIM Data | cycle count Authorized QTY Bug | 2022-02-11 13:11:06 | Low
Retail | Enhancement Related | 2021-11-24 15:54:13 | 739380 | 2021-11-24 19:54:13 | RMFCS Vendor Support | High |  | 37299 |  | SR 3-27806208921 |  |  | Carlos Costa | Urgent | auddin@panda.com.sa | Ayen Uddin | RMFCS Vendor Support | Ready for Deployment – Production | RMS | Cost showing in RMFCS Item supplier country screen with 3 decimal place need to increase up to 4 decimal. | 2022-02-16 10:49:42 | High
Supply Chain Oracle Inventory | Functional Issue | 2021-12-06 10:09:54 | 742972 | 2021-12-23 11:05:17 | RMFCS Vendor Support | High |  | 37882 |  | 3-28072010191 | No status changes since last RC update. | No status changes since last update WIP with ORC. | Carlos Costa | Medium | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | Pack Item and Pack component Item SOH Mismatch - Pack No# 3187590 Comp#449520 | 2022-02-11 13:13:19 | High
Retail |  | 2021-09-02 18:54:01 | 706055 | 2021-09-09 12:00:00 | RMFCS Vendor Support | Low |  | 38105 | Manon Brard | SR 3-26374302851 - BUG_33410682 | No status changes since last update WIP with ORC. Hi There is no new update, once the bug status changes it will change the status on this SR and I will provide an update on what has changed on the bug. For the time being the status remains: The associated bug has now been assigned to a developer and is in progress. You will be advised as soon as additional details become available. Regards Charles | No status changes since last update WIP with ORC. | Carlos Costa | Low | rmfcsptassets@panda.com.sa | RMFCS Project Team | No Agent | Pending With Vendor | RMS | PGL - Panda Issue 1461 - Transfer create from existing allows approval of transfer with quantity = 0 [SR 3-26374302851] | 2022-02-11 13:15:15 | Low
Retail |  | 2021-12-12 12:43:53 | 745076 | 2021-12-12 16:43:53 | RMFCS Vendor Support | High |  | 38209 |  | 3-28603554961 (RMFCS) ¦ 3-27979402561 (Assets) | 3-28603554961 New SR was created for this incidente last update : Hi José, It seems that a similar looking issue was already reported in December for this project. Oracle Operation will perform a lightly different SQL at your database, which was already approved in Bug 33662745 Update item_loc set receive_as_type = null where receive_as_type is not null and loc in (select store from store) and loc_type=’S’; We will keep you informed about the progress. Kind regards, André | New SR 3-28603554961 was created for this incidente last update : Hi José, I was informed by our development that a similar SR and Bug was already opened for your project. But I can leave this SR open if you like. Kind regards, André JOSE.RIBEIRO@RETAIL-CONSULT.COM - 20+ hours ago [Update from Customer] Hi André, Thanks for the info. We are waiting for the main issue to be fixed. You will let us knows by this SR, correct? Regarding data fix, until the issue is not fixed, how often will you perform the update again? Thank you. Regards, José | Jose Ribeiro | Urgent | ahmedkhan@panda.com.sa | Ateeq Khan | RMFCS Vendor Support | Pending With Vendor | RMS | 'Receive As' Type is updating for stores as well whereas should update only to warehouse through ILR ranging | 2022-02-15 18:12:21 | High
Retail |  | 2021-11-23 14:53:50 | 738970 | 2021-11-30 09:53:50 | RMFCS Vendor Support | Low |  | 38238 |  | 3-27999104161 | No status changes since last RC update. | No status changes since last RC update. | Carlos Costa | Low | dcitl@panda.com.sa | DC Inbound Ambient TL | RMFCS Vendor Support | Pending With Vendor | REIMCS | to arrange the SKU in sequence in PO (Oracle) | 2022-02-11 13:21:19 | Low
Supply Chain Oracle Inventory | Functional Issue | 2021-11-24 10:00:22 | 739184 | 2021-11-25 09:00:22 | RMFCS Vendor Support | High |  | 38433 |  | 3-28605495651 (Cloud); 3-28453924471 (Assets) | New SR 3-28605495651 created. Last update on old SR Hello Antonio, Thank you for your feedback. We have since created SR 3-28605495651 in order to pursue the issue with the RMFCS replenishment attributes induction web service with the Cloud team. Let's please keep the SR open for two days more in case of any further questions from Panda, and then we can close this SR. Kind regards, Rui Machado | New SR 3-28605495651 created. No status changes since last RC update. WIP with ORC | Carlos Costa | High | atkhan@panda.com.sa | Atif Khan | RMFCS Vendor Support | Pending With Vendor |  | repl_item_loc pickup_lead_time updated as 0 for most of DSD items. GMDH picks this as leadtime. | 2022-02-14 20:36:20 | High
Retail |  | 2021-12-17 13:07:48 | 747359 | 2021-12-23 12:00:00 | RMFCS Vendor Support | Low |  | 38510 |  | 3-26337055821 | No status changes since last update WIP with ORC. | No status changes since last update WIP with ORC. | Carlos Costa | Low | rmfcsptassets@panda.com.sa | RMFCS Project Team | RMFCS Vendor Support | Pending With Vendor | RMS | PGL - SR 3-26337055821 : UDA Length not checked in UI | 2022-02-11 13:22:47 | Low
Retail | Identity and Access | 2021-12-13 13:48:58 | 745541 | 2021-12-14 12:48:58 | RMFCS Vendor Support | High |  | 38377 |  | 3-28526010821 |  |  | Carlos Costa | High | rwarrier@panda.com.sa | Rajeev Warrier | RMFCS Vendor Support | Open | REIMCS | Negative SOH | 2022-02-16 08:59:57 | High
Supply Chain Oracle Procurement |  | 2021-12-26 10:30:59 | 750276 | 2021-12-28 16:30:59 | RMFCS Vendor Support | Medium |  | 38932 |  | 3-28136613361 (Assets), 3-28155641321 (Cloud) | New update on sr SR 3-28527985541 | New update on sr SR 3-28527985541-Incidente was pass to MOM Guna | Carlos Costa | Medium | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | When the Item Location status changes from Active to Inactive, the ILR upload does not check the Open PO/TO status | 2022-02-15 11:14:02 | Medium
Supply Chain Oracle Inventory |  | 2021-12-27 12:49:16 | 750700 | 2021-12-27 16:49:16 | RMFCS Vendor Support | High |  | 38958 |  | 3-28115296791 | No updates from Oacle after several updates from RC | No updates from Oacle after several updates from RC | Carlos Costa | Urgent | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | DC Receipt Quantity is double in RMFCS | 2022-02-11 13:24:20 | High
Retail | Functional Issue | 2022-01-12 09:40:22 | 756131 | 2022-01-19 13:41:00 | SIM Vendor Support Group | Low |  | 39934 |  | 3-28260764391 | No status changes since last update WIP with ORC. | No status changes since last update WIP with ORC. | Carlos Pinho | Low | wsobhi@panda.com.sa | Wael Kamal Sobhi | Oracle Services Management | Pending With Vendor | Oracle SIM Application | Stock Count QTY Issue | 2022-02-11 13:38:55 | Low
IT Operation Maintenance |  | 2021-12-30 14:05:47 | 751938 | 2022-01-06 09:05:47 | SIM Vendor Support Group | Low |  | 41570 |  | test3 |  |  | Carlos Pinho | Low | oraclesm@panda.com.sa | Oracle Services Management | SIM Vendor Support | Pending | Handheld | Integration Test between Mantis and MyService | 2022-02-15 21:01:35 | Low
Retail |  | 2022-01-04 13:54:31 | 753609 | 2022-01-11 08:55:00 | Integration Vendor Support Group | Low |  | 39610 |  | 3-28182380321 |  |  | Luis Martins | Low | integrationpt@panda.com.sa | Integration Project Team | RIB Vendor Support | Pending With Vendor | SABS | SABS interfaces ID64 (Items) and ID232 (Transfers) incorrectly use UDA DESC as UDA identifiers | 2022-02-14 19:22:56 | Low
Supply Chain Oracle Inventory | Functional Issue | 2022-01-17 16:30:55 | 757932 | 2022-01-17 20:30:55 | RMFCS Retail Finance and Pricing vendor support | High |  | 40231 |  | SR 3-28310232771 | No status changes since last RC update. | No status changes since last RC update. | Vitor Goncalves | Urgent | rvaidyanathan@panda.com.sa | Ramkumar Vaidyanathan | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor |  | SAIMPTLOGI Partial Load | 2022-02-11 13:42:26 | High
Retail | Application Performance | 2021-09-08 15:33:13 | 709566 | 2021-09-13 12:33:13 | RMFCS Retail Finance and Pricing vendor support | Medium |  | 40306 | Svyatoslav Tezin | 3-26956624811 | No status changes since last RC update. | No status changes since last RC update. | Vitor Goncalves | Medium | logichypercare@panda.com.sa | Logic Hypercare | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | RMS | ReSA Calculation of Item Total, Discount Total, Transaction Totals is not fully aligned with the SAIMPTLOGI batch | 2022-02-11 13:43:43 | Medium
Retail |  | 2022-01-10 17:41:45 | 755641 | 2022-01-10 21:41:45 | RMFCS Retail Finance and Pricing vendor support | High |  | 40307 |  | 3-28253155401 | No status changes since last RC update. | No status changes since last RC update. | Carlos Costa | Urgent | mbhussain@panda.com.sa | Mohammed Bakeer Hussain | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | REIMCS | Clearance event on Processing Status for long | 2022-02-03 14:30:49 | High
Retail |  | 2022-01-21 00:25:55 | 759162 | 2022-01-25 14:00:00 | RMFCS Vendor Support | High |  | 40401 |  |  |  |  | Carlos Pinho | Medium | noreply@uc4.com | Noreply | RMFCS Vendor Support | Pending | RMS | Alarm:'ORCA_SPFINDOCSCAL' RunID:'018288074' Client:'0001' | 2022-01-25 17:39:26 | High
Financials Oracle Payables | Functional Issue | 2022-01-29 05:03:05 | 761628 | 2022-01-29 09:03:05 | RMFCS Retail Finance and Pricing vendor support | High |  | 40890 |  | SR 3-28442894861 | No status changes since last update. WIP Guna & ORC. | No status changes since last update. WIP Guna & ORC. | Bruno Melo | Urgent | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor |  | Invoice Mismatch between RMFCS vs IMCS | 2022-02-11 13:46:39 | High
Retail | Identity and Access | 2022-02-01 09:25:06 | 762697 | 2022-02-02 08:25:06 | Integration Vendor Support Group | Low |  | 41268 |  |  |  |  | Carlos Costa | High | rwarrier@panda.com.sa | Rajeev Warrier | RIB Vendor Support | Open | RMS | Catch Wt item Mismatch | 2022-02-16 01:33:23 | Low
Retail | Identity and Access | 2022-02-01 10:05:54 | 762719 | 2022-02-07 14:05:54 | RMFCS Vendor Support | Low |  | 41105 |  | 3-28526010821 |  |  | Carlos Costa | Low | rwarrier@panda.com.sa | Rajeev Warrier | RMFCS Vendor Support | Open | WMS | Non Catch Wt Variance is in Decimals | 2022-02-14 15:13:32 | Low
Supply Chain Oracle Inventory |  | 2022-02-02 12:39:01 | 763241 | 2022-02-03 11:39:01 | Integration Vendor Support Group | High |  | 41108 |  | 3-27677928341 |  |  | Luis Martins | High | aalsaiyed@panda.com.sa | Amjad Saiyed | RIB Vendor Support | Pending With Vendor |  | Appointment not closed in MFCS though marked as P in iia.stg_manht_receipt_in | 2022-02-15 17:12:14 | High
Retail | Functional Issue | 2022-02-06 13:10:50 | 764475 | 2022-02-13 08:10:50 | RMFCS Vendor Support | Low |  | 41910 |  |  |  |  | Carlos Costa | Low | skhallaf@panda.com.sa | Sahar Hassan Khallaf | RMFCS Vendor Support | Open | RMS | Importation wrong average cost | 2022-02-16 10:28:25 | Low
Retail |  | 2022-02-13 14:31:34 | 767786 | 2022-02-14 13:31:34 | Integration Vendor Support Group | High |  | 41757 |  | 3-28615074371 |  |  | Luis Martins | High | jkandiyil@panda.com.sa | Jabir Kummankott Kandiyil | RIB Vendor Support | Pending With Vendor | WMS | Unprocessed records under MANHT_STG_PIX_IN | 2022-02-15 15:31:39 | High
Supply Chain Oracle Inventory |  | 2022-02-14 17:26:14 | 768287 | 2022-02-17 15:22:09 | Integration Vendor Support Group | Low |  | 41800 |  |  |  |  | Luis Martins | Low | aalsaiyed@panda.com.sa | Amjad Saiyed | RIB Vendor Support | Open |  | ID 228 sequence of processing | 2022-02-16 11:08:09 | Low
Supply Chain Oracle Inventory |  | 2022-02-14 20:54:51 | 768299 | 2022-02-21 12:00:00 | Integration Vendor Support Group | Low |  | 41819 |  | 3-28605570711 |  |  | Luis Martins | Low | pedro.a.alves@oracle.com | Pedro.a.alves | RIB Vendor Support | Pending With Vendor |  | ID274 - Open purchase orders missing shipments and dates | 2022-02-15 17:56:14 | Medium
Supply Chain Oracle Inventory | Functional Issue | 2022-02-16 09:29:56 | 768827 | 2022-02-17 08:30:35 | Integration Vendor Support Group | High | [6 empty] | Carlos Costa | High | atkhan@panda.com.sa | Atif Khan | RIB Vendor Support | Open |  | ID 298 item information not flowing to GMDH when the planning group field is changed or updated. | 2022-02-16 11:10:35 | High
Retail | Functional Issue | 2022-02-16 09:48:27 | 768844 | 2022-02-22 13:48:29 | RMFCS Vendor Support | Low |  | 41917 |  |  |  |  | Carlos Costa | Low | jjaleel@panda.com.sa | Jahanaz Jaleel | RMFCS Vendor Support | Open | RMS | pack comp soh issue | 2022-02-16 11:30:29 | Low