## 202220128
Category | Classification | Created Time | Ticket Id | Due by Time | Group | Impact | Item | Mantis ID Ref. | Agent Name | Oracle SR | UPDATE AT 20220127 | UPDATE AT 20220128 | ORC L2 Agents | Priority | Requester Email | Requester Name | Agent | Status | Sub-Category | Subject | Last Updated Time | Urgency
Retail |  | 2021-09-14 17:57:02 | 712433 | 2021-09-21 12:00:00 | RMFCS Vendor Support | Medium |  | 34586 |  | SR 3-27167309171 | No status changes since last update | Last update from Oracle after RC update: JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi Marcus, Thank you for the update.Please keep us posted if there is any new update. Best regards, Jose Aguiar Oracle Support - 21+ hours ago [Notes] Hi Jose, I've now raised a product bug as requested by the Dev team. I will keep you updated as additional information comes available. Thanks, Marcus | Vitor Goncalves | Low | rmfcsptassets@panda.com.sa | RMFCS Project Team | RMFCS Vendor Support | Pending With Vendor | RMS | RMFCS - CW items - Case Weight definition is not mandatory | 2022-01-24 12:55:05 | Medium
Financials Oracle Receivables |  | 2021-09-30 11:14:31 | 719205 | 2021-09-30 15:14:31 | RMFCS Retail Finance and Pricing vendor support | High |  | 34840 |  | SR 3-27241839551 | No status changes since last update. checking with dev | Last update from Oracle after RC update: JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi Srinivas (Rene), Thank you for the update. Please keep us posted since the severity is 1. Best regards, José Aguiar Oracle Support - Tuesday [Notes] checking with dev Oracle Support - 6 days ago [Notes] update received checking with development JOSE.AGUIAR@RETAIL-CONSULT.COM - 7 days ago [Update from Customer] Hi Srinivas (Rene), Thank you for the update. Please keep us posted since the severity is 1. Best regards, José Aguiar | Bruno Melo | Urgent | rlasmal@panda.com.sa | Ram Lamsal | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor |  | Unable to resolve invoices due to qty Decimal issue | 2022-01-24 12:59:01 | High
Retail |  | 2021-10-06 04:04:18 | 721019 | 2021-10-10 14:00:00 | RMFCS Vendor Support | Medium |  | 35030 |  | SR 3-27369964201 | Hi Jose, As my colleague already mentioned, target date for mfcs 19.2.011 is 07 Feb 2022. So expect an update on that date regarding fix release. Best Regards, Alexandru Udrea Global Software Support ¦ Retail | Hi Jose, As my colleague already mentioned, target date for mfcs 19.2.011 is 07 Feb 2022. So expect an update on that date regarding fix release. Best Regards, Alexandru Udrea Global Software Support ¦ Retail | Carlos Costa | Medium | pbsantos@panda.com.sa | Percival Santos | RMFCS Vendor Support | Pending With Vendor | RMS | Unable to delete Cost Change with Worksheet and Submitted statuses under user ID 20963 | 2022-01-24 13:01:00 | Medium
Retail |  | 2021-09-12 11:16:55 | 711008 | 2021-09-16 15:16:55 | RMFCS Retail Finance and Pricing vendor support | High |  | 35454 | John Jones | SR 3-27240525201 | No status changes since last RC update | No status changes since last RC update | Bruno Melo | Low | rlasmal@panda.com.sa | Ram Lamsal | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | REIMCS | ReIM - unable to continue invoice creation after clicking 'Save and Add another' | 2022-01-26 14:31:10 | Medium
Retail |  | 2021-10-11 08:59:33 | 722915 | 2021-10-13 14:59:33 | RMFCS Vendor Support | Low |  | 35555 |  | SR 3-27384206081 | No status changes since last update | No status changes since last RC update | Luis Martins | Medium | logicsupport@panda.com.sa | Logic Support | RMFCS Vendor Support | Pending With Vendor | RMS | ReceivingCre - [E] Error ORA-01476: divisor is equal to zero returned by program unit | 2022-01-26 14:25:47 | Low
Retail |  | 2021-10-14 15:05:54 | 724576 | 2021-10-14 19:05:54 | RMFCS Retail Finance and Pricing vendor support | Medium |  | 35567 |  | SR 3-27449790531 / Severity 1 SR 3-27665894791 | No status changes since last RC update | No status changes since last RC update : Hi Bruno Followed up with DEV team to share ETA for bug, will keep you updated Best regards Srinivas Gadde (SriDivya) | Bruno Melo | Urgent | rlasmal@panda.com.sa | Ram Lamsal | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | REIMCS | In Summary Matching screen, the receipt Qty is showing negative value | 2022-01-24 13:07:04 | Medium
Retail |  | 2021-10-17 12:48:01 | 725494 | 2021-10-21 16:48:01 | RMFCS Vendor Support | Low |  | 35667 |  | 3-27606141781 | No status changes since last RC update | No status changes since last RC update | Bruno Melo | Low | rlasmal@panda.com.sa | Ram Lamsal | RMFCS Vendor Support | Pending With Vendor | REIMCS | Unable to fetch data on discrepancy review list screen. | 2022-01-26 14:35:13 | Low
Financials Oracle Receivables | Functional Issue | 2021-11-01 14:22:17 | 731214 | 2021-11-08 09:22:17 | RMFCS Vendor Support | High |  | 36490 |  | SR 3-27596400571 | No status changes since last RC update | No status changes since last RC update | Bruno Melo | Low | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | User Unable to Match the Invoice with Receipt - Shows Tax Discrepancy | 2022-01-26 14:33:54 | High
Supply Chain Oracle Procurement |  | 2021-11-15 10:50:01 | 735830 | 2021-11-17 16:50:01 | RMFCS Vendor Support | Low |  | 36871 |  | SR 3-27696704841 | Last update from Oracle- Hi Vitor The current ETC is the 28th Jan. I will advise if this changes | Last update in the SR: JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi all, Please keep us posted about the details of the ETC. Thank you. Best regards, José Aguiar Oracle Support - 11 days ago [Notes] Hi Vitor The current ETC is the 28th Jan. I will advise if this changes VITOR.GONCALVES@RETAIL-CONSULT.COM - 12 days ago [Update from Customer] Hello, Can you please confirm when will be the next patch release mentioned? Thank you in advance. Best regards, Vitor | Carlos Costa | Medium | mraza@panda.com.sa | Mohd Raza | RMFCS Vendor Support | Pending With Vendor |  | Item Short Description Change in Item is not cascaded to Item Location Level | 2022-01-24 13:20:52 | Low
Retail | Environment Issue | 2021-11-22 10:57:33 | 738440 | 2022-01-25 11:29:27 | RMFCS Retail Finance and Pricing vendor support | Medium |  | 37134 |  | No SR Created | Oracle Services Management added a public note a month ago (Wed, 1 Dec, 2021 at 13:55) Notified to : rpcsvsg@panda.com.sa This request has been shared with Mike and Kimberley in order to check how to provide the information and also develop an operational process that Panda can follow every time that is necessary. Waiting update from them in order to update the ticket. | Oracle Services Management added a public note a month ago (Wed, 1 Dec, 2021 at 13:55) Notified to : rpcsvsg@panda.com.sa This request has been shared with Mike and Kimberley in order to check how to provide the information and also develop an operational process that Panda can follow every time that is necessary. Waiting update from them in order to update the ticket. | Second hoice | High | jalam@panda.com.sa | Junaid Alam | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | RMS | Cloud Patch deployment log | 2022-01-24 12:37:27 | High
Financials Oracle Receivables |  | 2021-11-28 17:45:33 | 740551 | 2021-11-28 21:45:33 | RMFCS Vendor Support | High |  | 37506 |  | SR 3-27832605471 | No status changes since last update | Last update in the SR: JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi, Could you please let us know if there is any new update. There is any Estimated Time of Arrival (ETA) on when the patch will be available for customer download. Thank you. Best regards, Jose Aguiar Oracle Support - 7 days ago [Notes] Hi Guna , Thank you for provided data. Will get back to you on this next week. Best Regards, Alexandru Udrea Global Software Support ¦ Retail | Carlos Costa | Urgent | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | Receiver Cost Adjustment (RCA) done in RMFCS Does Not Recalculate WAC | 2022-01-24 13:24:33 | High
Financials Oracle Payables | Functional Issue | 2021-11-30 10:22:29 | 740964 | 2021-11-30 14:22:29 | RMFCS Retail Finance and Pricing vendor support | High |  | 37587 |  | SR 3-27857339571 | No status changes since last RC update | No status changes since last RC update | Bruno Melo | Urgent | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor |  | After performing RCA, ReIM EDI Injector Batch Inserts Reason Code As Null For Debit Memo Cost Document- Failed in Invoice Posting | 2022-01-26 14:36:48 | High
Retail | Functional Issue | 2021-11-25 14:14:22 | 739680 | 2021-12-02 09:14:22 | RMFCS Vendor Support | Medium |  | 37609 |  | 3-24301935601 | No status changes since last RC update | Last RC update in the SR: JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi, Could you please let us know if there is any new update since last 6 days ago? There is any Estimated Time of Arrival (ETA) on when the patch will be available for customer download. Thank you. Best regards, Jose Aguiar | Carlos Costa | Low | rmfcsptassets@panda.com.sa | RMFCS Project Team | RMFCS Vendor Support | Pending With Vendor | RMS | Catch Weight Sale Types are not validating Standard UOM in Item Creation | 2022-01-24 13:40:02 | Low
Retail |  | 2021-11-29 08:37:05 | 740623 | 2021-12-05 12:37:05 | SIM Vendor Support Group | Low |  | 37640 |  | SR 3-27874541491 | No status changes since last update | Last update from RC in the SR: JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi Alexandru Udrea, Thank you for the update, please keep us posted if there is any new information. Best regards, José Aguiar | Carlos Pinho | Low | mamahmoud@panda.com.sa | Mahmoud Mostafa | SIM Vendor Support | Pending With Vendor | Oracle SIM Data | cycle count Authorized QTY Bug | 2022-01-26 14:53:54 | Low
Supply Chain Oracle Inventory | Functional Issue | 2021-12-06 10:09:54 | 742972 | 2021-12-23 11:05:17 | RMFCS Vendor Support | High |  | 37882 |  | 3-28072010191 | No status changes since last update | Last update from RC in the SR: JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi, Could you please let us know if there is any new update. There is any Estimated Time of Arrival (ETA) on when the patch will be available for customer download. Thank you. Best regards, Jose Aguiar | Carlos Costa | Medium | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | Pack Item and Pack component Item SOH Mismatch - Pack No# 3187590 Comp#449520 | 2022-01-24 13:55:47 | High
Retail |  | 2021-09-02 18:54:01 | 706055 | 2021-09-09 12:00:00 | RMFCS Vendor Support | Low |  | 38105 | Manon Brard | SR 3-26374302851 - BUG_33410682 | No status changes since last update | Last update from RC in the SR: JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi Charles, Thank you for the update, please keep us posted if there is any new information. Best regards, José Aguiar | Carlos Costa | Low | rmfcsptassets@panda.com.sa | RMFCS Project Team | No Agent | Pending With Vendor | RMS | PGL - Panda Issue 1461 - Transfer create from existing allows approval of transfer with quantity = 0 [SR 3-26374302851] | 2022-01-24 13:58:39 | Low
Retail |  | 2021-11-23 14:53:50 | 738970 | 2021-11-30 09:53:50 | RMFCS Vendor Support | Low |  | 38238 |  | 3-27999104161 | No status changes since last update | Last update from RC in the SR: JOSE.AGUIAR@RETAIL-CONSULT.COM - < 1 min ago [Update from Customer] Hi Gabriel, Thank you for the update, please keep us posted if there is any new information. Best regards, José Aguiar | Carlos Costa | Low | dcitl@panda.com.sa | DC Inbound Ambient TL | RMFCS Vendor Support | Pending With Vendor | REIMCS | to arrange the SKU in sequence in PO (Oracle) | 2022-01-24 14:01:01 | Low
Retail |  | 2021-12-17 13:07:48 | 747359 | 2021-12-23 12:00:00 | RMFCS Vendor Support | Low |  | 38510 |  | 3-26337055821 | No status changes since last update | No status changes since last update | Carlos Costa | Low | rmfcsptassets@panda.com.sa | RMFCS Project Team | RMFCS Vendor Support | Pending With Vendor | RMS | PGL - SR 3-26337055821 : UDA Length not checked in UI | 2022-01-24 14:03:36 | Low
Supply Chain Oracle Procurement |  | 2021-12-26 10:30:59 | 750276 | 2021-12-28 16:30:59 | RMFCS Vendor Support | Medium |  | 38932 |  | 3-28136613361 (Assets), 3-28155641321 (Cloud) | No status changes since last update. WIP | No status changes since last update. WIP | Carlos Costa | Medium | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | When the Item Location status changes from Active to Inactive, the ILR upload does not check the Open PO/TO status | 2022-01-26 17:28:56 | Medium
Supply Chain Oracle Inventory |  | 2021-12-27 12:49:16 | 750700 | 2021-12-27 16:49:16 | RMFCS Vendor Support | High |  | 38958 |  | 3-28115296791 | No updates fromOacle after several updates from RC | No updates fromOacle after several updates from RC | Carlos Costa | Urgent | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | DC Receipt Quantity is double in RMFCS | 2022-01-24 14:12:37 | High
Supply Chain Oracle Procurement | Functional Issue | 2022-01-03 09:44:33 | 753078 | 2022-01-03 13:44:33 | RMFCS Vendor Support | High |  | 39475 |  | 3-28165021621 | No status changes since last update. WIP | No status changes since last update. WIP Guna -Junaid Alam | Carlos Costa | Urgent | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Vendor Support | Pending With Vendor |  | Import Purchase Order created via Induction process is defaulting wrong exchange rate | 2022-01-25 14:58:48 | High
Financials Oracle Payables |  | 2022-01-09 13:13:21 | 755170 | 2022-01-10 15:04:54 | RMFCS Retail Finance and Pricing vendor support | High |  | 39795 |  | SR 3-28228638111 | No status changes since last update. WIP | No status changes since last update. WIP Guna -Junaid Alam | Carlos Costa | Urgent | gpappannan@panda.com.sa | Gunasekaran Pappannan | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor |  | Invoice Matching - Incorrect Quantity default from Receipt | 2022-01-24 14:57:45 | High
Retail | Functional Issue | 2022-01-12 09:40:22 | 756131 | 2022-01-19 13:41:00 | SIM Vendor Support Group | Low |  | 39934 |  | 3-28260764391 | Last update in the SR (WIP) - Hi Jose, I tested and reproduced the issue. Observe Total Counted Quantity in the screen is 508. If using the recounted qty 17 x pack of 24 + 11 x pack of 6 + 17 = 484 If using the initial counted qty 18 x pack of 24 + 11 x pack of 6 + 17 = 508 Reference: Test_Case_3-28260764391.xls At this point we are discussing internally to clarify with FA the correct behavior. This is because on the other new scenario (for recount quantity) I see total qty is taking only recount qty while on this new SR scenario is using stock count qty. e.g 3-27874541491: Stock Count is not considering counted quantities from Pack's (scenario for recount). Will let you know as soon as I have news. Best Regards, Alexandru Udrea Global Software Support ¦ Retail | No status changes since last update. WIP | Carlos Pinho | Low | wsobhi@panda.com.sa | Wael Kamal Sobhi | Oracle Services Management | Pending With Vendor | Oracle SIM Application | Stock Count QTY Issue | 2022-01-21 14:40:15 | Low
Retail | Functional Issue | 2022-01-12 14:55:57 | 756343 | 2022-01-17 11:55:57 | RMFCS Retail Finance and Pricing vendor support | Medium |  | 39993 |  | SR 3-28310830801 | No status changes since last update from RC. | No status changes since last update from RC. | Carlos Pinho | Medium | rvaidyanathan@panda.com.sa | Ramkumar Vaidyanathan | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | RMS | Store day summary still showing errors for Deleted transactions | 2022-01-24 15:04:52 | Medium
Supply Chain Oracle Inventory | Functional Issue | 2022-01-17 16:30:55 | 757932 | 2022-01-17 20:30:55 | RMFCS Retail Finance and Pricing vendor support | High |  | 40231 |  | SR 3-28310232771 | No status changes since last update. Request is still in Development. | No status changes since last update. WIP | Vitor Goncalves | Urgent | rvaidyanathan@panda.com.sa | Ramkumar Vaidyanathan | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor |  | SAIMPTLOGI Partial Load | 2022-01-24 15:11:51 | High
Retail | Application Performance | 2021-09-08 15:33:13 | 709566 | 2021-09-13 12:33:13 | RMFCS Retail Finance and Pricing vendor support | Medium |  | 40306 | Svyatoslav Tezin | 3-26956624811 | No changes made since last RC update | No changes made since last RC update | Vitor Goncalves | Medium | logichypercare@panda.com.sa | Logic Hypercare | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | RMS | ReSA Calculation of Item Total, Discount Total, Transaction Totals is not fully aligned with the SAIMPTLOGI batch | 2022-01-24 15:21:16 | Medium
Retail |  | 2022-01-10 17:41:45 | 755641 | 2022-01-10 21:41:45 | RMFCS Retail Finance and Pricing vendor support | High |  | 40307 |  | 3-28253155401 | Last update in the SR (WIP) : Dear Pedro, We are currently discussing this issue internally. I will update the SR when I have more information available. I appreciate your patience with this issue. Thank you and best regards, Sharma Oracle Software Support | No status changes since last update. WIP | Carlos Costa | Urgent | mbhussain@panda.com.sa | Mohammed Bakeer Hussain | RMFCS Retail Finance and Pricing Vendor Support | Pending With Vendor | REIMCS | Clearance event on Processing Status for long | 2022-01-21 15:01:12 | High